## Sheet1
ProEnergy EPC | [11 empty] | ProEnergy EPC
Job Description: |  |  | "Two Pratt Whitney FT4 Twin Paks SC" | [8 empty] | Job Description: |  |  | "Two Pratt Whitney FT4 Twin Paks SC"
RECAP OF COST ESTIMATE | [11 empty] | RECAP OF COST ESTIMATE | [11 empty] | ESTIMATED VALUE OF DERWICK PERFORMED CIVIL WORK
(1,000'S) | [11 empty] | (1,000'S) | [11 empty] | Status Date: 11 Oct 2011
Project Name: |  |  | Barinas I Power Plant |  |  |  |  | Date: | 40820 |  |  | Project Name: |  |  | Barinas I Power Plant |  |  |  |  | Date: | 40808 |  |  | (1,000'S)
Customer: |  |  | PDVSA |  |  |  |  | Quote No: | T 1003 |  |  | Customer: |  |  | PDVSA |  |  |  |  | Quote No: | T 1003 - 6
Location: |  |  | Barinas, Venn |  |  |  |  | Est By: |  |  |  | Location: |  |  | Barinas, Venn |  |  |  |  | Est By: | RHL Update
Bid Due Date: | [7 empty] | RHL-civil by Derwick |  |  |  | Bid Due Date: |  |  | 40458
I. Balance of Plant | [9 empty] | US $ | BsF | I. Balance of Plant | [9 empty] | US $ | BsF | Equivalent USD | US $ | BsF
| 100 Civil Structural | [9 empty] | 8.5 |  | 100 Civil Structural | [9 empty] | 8.5
|  | 101 | Site Preparation |  |  |  | 0 | calc |  | 0 | 0 |  |  | 101 | Site Preparation |  |  |  | 336.4504 | calc |  | 84.1126 | 2144.8711 | 336.4504 | 84.1126 | 2144.8711
|  | 102 | Excavation - Fill |  |  | Mhrs | 0 | calc |  | 0 | 0 |  |  | 102 | Excavation - Fill |  |  | Mhrs | 231.8933 | calc |  | 57.9733 | 1478.32 | 231.8933 | 57.9733 | 1478.32
|  | 103 | Concrete Foundations |  |  | 0 | 0 | calc |  | 0 | 0 |  |  | 103 | Concrete Foundations |  |  | 20857.963 | 3337.2741 | calc |  | 834.3185 | 21275.1222 | 3337.2741 | 834.3185 | 21275.1222
|  | 104 | Concrete Pilings |  |  |  | 0 | calc | [5 empty] | 104 | Concrete Pilings |  |  |  | 0 | calc |  |  |  | 0 | 0 | 0
|  | 105 | Paving Asphalt - Concrete |  |  |  | 0 | calc |  | 0 | 0 |  |  | 105 | Paving Asphalt - Concrete |  |  |  | 1205.3333 | calc |  | 301.3333 | 7684 | 1205.3333 | 301.3333 | 7684
|  | 106 | Gravel - Sand |  |  |  | 0 | calc |  | 0 | 0 |  |  | 106 | Gravel - Sand |  |  |  | 260.5278 | calc |  | 65.1319 | 1660.8646 | 260.5278 | 65.1319 | 1660.8646
|  | 107 | Structual Steel |  |  |  | 95 | calc |  | 23.75 | 605.625 |  |  | 107 | Structual Steel |  |  |  | 95 | calc |  | 23.75 | 605.625 | 0 | 0 | 0
|  | 108 | Fencing |  |  |  | 0 | calc |  | 0 | 0 |  |  | 108 | Fencing |  |  |  | 207.7 | calc |  | 51.925 | 1324.0875 | 207.7 | 51.925 | 1324.0875
|  | 109 | Architectual Treatment |  |  |  | 0 | calc | [5 empty] | 109 | Architectual Treatment |  |  |  | 0 | calc |  |  |  | 0 | 0 | 0
|  | 110 | Evaporation Pond |  |  |  | 0 | calc | [5 empty] | 110 | Evaporation Pond |  |  |  | 0 | calc |  |  |  | 0 |  | 0
[7 empty] | 95 |  | 95 | [9 empty] | 5674.1789 |  | 5674.1789 |  |  | 5579.1789 | 1394.7947 | 35567.2654
| 200 Buildings | [5 empty] | 331.25 | calc | 331.25 | 331.25 |  |  | 200 Buildings | [5 empty] | 331.25 | calc | 331.25 | 331.25 |  | 0 | 0 | 0
[24 empty] | 0 | 0 | 0
| 300 Mechanical |  |  |  |  | Mhrs | [6 empty] | 300 Mechanical |  |  |  |  | Mhrs
|  | 310 | Major Mechanical Equipment |  |  |  | 4644 | calc |  | 4644 |  |  |  | 310 | Major Mechanical Equipment |  |  |  | 4834 | calc |  | 4834 |  | 190 | 190 | 0
|  | 320 | Pipe, Valves & Fitting labor |  |  | 35100 | 2036.4704 | calc |  | 509.1176 | 12982.4989 |  |  | 320 | Pipe, Valves & Fitting labor |  |  | 35100 | 2036.4704 | calc |  | 509.1176 | 12982.4989 | 0 | 0 | 0
|  | 330 | Mechanical Subcontractor |  |  | 28062 | 1628.132 | calc |  | 407.033 | 10379.3414 |  |  | 330 | Mechanical Subcontractor |  |  | 28062 | 1628.132 | calc |  | 407.033 | 10379.3414 | 0 | 0 | 0
|  | 340 | Pipe, Valves & Fitting Material |  |  |  | 900 | calc |  | 900 |  |  |  | 340 | Pipe, Valves & Fitting Material |  |  |  | 900 | calc |  | 900 |  | 0 | 0 | 0
[7 empty] | 9208.6024 |  | 9208.6024 | [9 empty] | 9398.6024 |  | 9398.6024 |  |  | 190 | 190 | 0
| 400 Electrical | [11 empty] | 400 Electrical
|  | 410 | Major Electrical Equipment |  |  |  | 966.2 | calc |  | 966.2 |  |  |  | 410 | Major Electrical Equipment |  |  |  | 966.2 | calc |  | 966.2 |  | 0 | 0 | 0
|  | 420 | Substation Equipment |  |  |  | 681.6 | calc |  | 681.6 |  |  |  | 420 | Substation Equipment |  |  |  | 681.6 | calc |  | 681.6 |  | 0 | 0 | 0
|  | 430 | Plant Electrical Subcontractor |  |  | 19148.4 | 1110.9729 | calc |  | 277.7432 | 7082.4525 |  |  | 430 | Plant Electrical Subcontractor |  |  | 19148.4 | 1110.9729 | calc |  | 277.7432 | 7082.4525 | 0 | 0 | 0
|  | 440 | Substation Subcontractor |  |  | 6544.8 | 379.7234 | calc |  | 94.9309 | 2420.7367 |  |  | 440 | Substation Subcontractor |  |  | 6544.8 | 379.7234 | calc |  | 94.9309 | 2420.7367 | 0 | 0 | 0
|  | 450 | Conduit, Cable & Wire Material |  |  |  | 900 | calc |  | 900 |  |  |  | 450 | Conduit, Cable & Wire Material |  |  |  | 900 | calc |  | 900 |  | 0 | 0 | 0
|  | 460 | Conduit, Cable & Wire Labor |  |  | 28080 | 1629.1763 | calc |  | 407.2941 | 10385.9991 |  |  | 460 | Conduit, Cable & Wire Labor |  |  | 28080 | 1629.1763 | calc |  | 407.2941 | 10385.9991 | 0 | 0 | 0
[7 empty] | 5667.6727 |  | 5667.6727 | [9 empty] | 5667.6727 |  | 5667.6727 |  |  | 0 | 0 | 0
| 500 Instrumentation | [11 empty] | 500 Instrumentation
|  | 510 | CEMS |  |  |  | 0 | calc | [5 empty] | 510 | CEMS |  |  |  | 0 | calc |  |  |  | 0 | 0 | 0
|  | 520 | Plant Instrumentation |  |  |  | 125 | calc | [5 empty] | 520 | Plant Instrumentation |  |  |  | 125 | calc |  |  |  | 0 | 0 | 0
|  | 530 | Instrumentation Subcontractor |  |  | 1440 | 83.5475 | calc | [5 empty] | 530 | Instrumentation Subcontractor |  |  | 1440 | 83.5475 | calc |  |  |  | 0 | 0 | 0
[7 empty] | 208.5475 |  | 208.5475 | 208.5475 | [8 empty] | 208.5475 |  | 208.5475 | 208.5475 |  | 0 | 0 | 0
| 600 DCS System / Communications | [11 empty] | 600 DCS System / Communications
|  | 610 | Hardware / Software |  |  |  | 685 | calc | [5 empty] | 610 | Hardware / Software |  |  |  | 685 | calc |  |  |  | 0 | 0 | 0
|  | 620 | Telephone System |  |  |  | 15 | calc | [5 empty] | 620 | Telephone System |  |  |  | 15 | calc |  |  |  | 0 | 0 | 0
|  | 630 | Public Address System |  |  |  | 15 | calc | [5 empty] | 630 | Public Address System |  |  |  | 15 | calc |  |  |  | 0 | 0 | 0
|  | 640 | TV / Security |  |  |  | 0 | calc | [5 empty] | 640 | TV / Security |  |  |  | 0 | calc |  |  |  | 0 | 0 | 0
[7 empty] | 715 |  | 715 | 715 | [8 empty] | 715 |  | 715 | 715 |  | 0 | 0 | 0
| 700 Plant Erection | [11 empty] | 700 Plant Erection
|  | 700 | Plant Erection |  |  | 21600 | 1253.2126 | calc | [5 empty] | 700 | Plant Erection |  |  | 21600 | 1253.2126 | calc |  |  |  | 0 | 0 | 0
|  | 750 | Plant Dismantling |  |  |  | 0 | plgd/1000 | [5 empty] | 750 | Plant Dismantling |  |  |  | 0 | plgd/1000 |  |  |  | 0 | 0 | 0
|  | 755 | Plant Dismantling Labor |  |  |  | 0 | plgd/1000 | [5 empty] | 755 | Plant Dismantling Labor |  |  |  | 0 | plgd/1000 |  |  |  | 0 | 0 | 0
|  |  |  | Total El/Mech Mhrs |  | 139975.2 | 1253.2126 |  | 1253.2126 | 313.3031 | 7989.2301 |  |  |  |  | Total El/Mech Mhrs |  | 139975.2 | 1253.2126 |  | 1253.2126 | 313.3031 | 7989.2301 | 0 | 0 | 0
| 800 Equipment Rental | [5 empty] | 988.25 | calc | 988.25 | 247.0625 | 6300.0938 |  | 800 Equipment Rental | [5 empty] | 988.25 | calc | 988.25 | 247.0625 | 6300.0938 | 0 | 0 | 0
[24 empty] | 0 | 0 | 0
| 900 Painting | [5 empty] | 285 | calc | 285 | 71.25 | 1816.875 |  | 900 Painting | [5 empty] | 285 | calc | 285 | 71.25 | 1816.875 | 0 | 0 | 0
[24 empty] | 0 | 0 | 0
| 1000 Transportation | [11 empty] | 1000 Transportation
|  | 1001 | US Inland Transportation |  |  |  | 608.12 | calc |  | 608.12 |  |  |  | 1001 | US Inland Transportation |  |  |  | 617.12 | calc |  | 617.12 |  | 9 | 9 | 0
|  | 1002 | Ocean/Air Freight |  |  |  | 600 | plgd /1000 |  | 600 |  |  |  | 1002 | Ocean/Air Freight |  |  |  | 600 | plgd /1000 |  | 600 |  | 0 | 0 | 0
|  | 1003 | Destination Inland Freight |  |  |  | 400 | plgd /1000 |  |  | 3400 |  |  | 1003 | Destination Inland Freight |  |  |  | 400 | plgd /1000 |  |  | 3400 | 0 | 0 | 0
|  | 1004 | Customs / Duties (plant equip & mat'l) |  |  |  | 0 | plgd /1000 | [5 empty] | 1004 | Customs / Duties (plant equip & mat'l) |  |  |  | 0 | plgd /1000 |  |  |  | 0 | 0 | 0
|  | 1005 | Unload & Receive Mat'l at Site (Relocate FT4's) |  |  |  | 200 | plgd /1000 |  |  | 1700 |  |  | 1005 | Unload & Receive Mat'l at Site (Relocate FT4's) |  |  |  | 200 | plgd /1000 |  |  | 1700 | 0 | 0 | 0
|  | 1006 | Receive, Inspect, Inventory |  |  |  | 0 | plgd /1000 | [5 empty] | 1006 | Receive, Inspect, Inventory |  |  |  | 0 | plgd /1000 |  |  |  | 0 | 0 | 0
|  | 1007 | Storage of FT4 Equipment & GSU's) |  |  |  | 150 | plgd /1000 |  |  | 1275 |  |  | 1007 | Storage of FT4 Equipment & GSU's) |  |  |  | 150 | plgd /1000 |  |  | 1275 | 0 | 0 | 0
|  | 1008 | Local Registrations Fees, License, Etc. |  |  |  | 0 | plgd /1000 | [5 empty] | 1008 | Local Registrations Fees, License, Etc. |  |  |  | 0 | plgd /1000 |  |  |  | 0 | 0 | 0
|  | 1009 | Transport of Damaged Goods for Repair |  |  |  | 0 | plgd /1000 | [5 empty] | 1009 | Transport of Damaged Goods for Repair |  |  |  | 0 | plgd /1000 |  |  |  | 0 | 0 | 0
[7 empty] | 1958.12 |  | 1958.12 | [9 empty] | 1967.12 |  | 1967.12 |  |  | 9 | 9 | 0
| 1100 Site Costs | [5 empty] | 623.8 | calc | 623.8 |  | 5302.3 |  | 1100 Site Costs | [5 empty] | 623.8 | calc | 623.8 |  | 5302.3 | 0 | 0 | 0
[24 empty] | 0 | 0 | 0
| 1200 Engineering | [11 empty] | 1200 Engineering
|  | 1201 | EPC Eng Labor |  |  |  | 1205 | calc |  | 1205 |  |  |  | 1201 | EPC Eng Labor |  |  |  | 990 | calc |  | 990 |  | -215 | -215 | 0
|  | 1202 | Local Eng |  |  |  | 360 | calc |  | 360 |  |  |  | 1202 | Local Eng |  |  |  | 360 | calc |  | 360 |  | 0 | 0 | 0
[7 empty] | 1565 |  | 1565 | 1565 | [8 empty] | 1350 |  | 1350 | 1350 |  | -215 | -215 | 0
| 1300 Project Management | [11 empty] | 1300 Project Management
|  | 1310 | Project & Construction |  |  |  | 2054 | calc | [5 empty] | 1310 | Project & Construction |  |  |  | 2054 | calc |  |  |  | 0 | 0 | 0
|  | 1320 | Inspectors |  |  |  | 368 | calc | [5 empty] | 1320 | Inspectors |  |  |  | 368 | calc |  |  |  | 0 | 0 | 0
[7 empty] | 2422 |  | 2422 | 2422 | [8 empty] | 2422 |  | 2422 | 2422 |  | 0 | 0 | 0
| 1400 Travel & Perdiem | [5 empty] | 892.75 | calc |  |  |  |  | 1400 Travel & Perdiem | [5 empty] | 892.75 | calc |  |  |  | 0 | 0 | 0
|  | 1410 | Project Meal Expense |  |  |  | 0 | calc | [5 empty] | 1410 | Project Meal Expense |  |  |  | 0 | calc |  |  |  | 0 | 0 | 0
[7 empty] | 892.75 |  | 892.75 | 892.75 | [8 empty] | 892.75 |  | 892.75 | 892.75 |  | 0 | 0 | 0
| 1500 Technical Reps |  |  |  |  | $/day | [6 empty] | 1500 Technical Reps |  |  |  |  | $/day
|  | 1501 | GTG Tech Rep |  | 150 | 2000 | 300 | plgd /1000 | [5 empty] | 1501 | GTG Tech Rep |  | 150 | 2000 | 300 | plgd /1000 |  |  |  | 0 | 0 | 0
|  | 1502 | Fire Water |  | 0 | 2000 | 0 | plgd /1000 | [5 empty] | 1502 | Fire Water |  | 0 | 2000 | 0 | plgd /1000 |  |  |  | 0 | 0 | 0
|  | 1503 | Gas Compressor |  | 0 | 2000 | 0 | plgd /1000 | [5 empty] | 1503 | Gas Compressor |  | 0 | 2000 | 0 | plgd /1000 |  |  |  | 0 | 0 | 0
|  | 1504 | Chiller |  | 0 | 2000 | 0 | plgd /1000 | [5 empty] | 1504 | Chiller |  | 0 | 2000 | 0 | plgd /1000 |  |  |  | 0 | 0 | 0
|  | 1505 | Water Treatment |  | 15 | 1800 | 27 | plgd /1000 | [5 empty] | 1505 | Water Treatment |  | 15 | 1800 | 27 | plgd /1000 |  |  |  | 0 | 0 | 0
|  | 1506 | Commission / S/U / Trng |  | 80 | 1800 | 144 | plgd /1000 | [5 empty] | 1506 | Commission / S/U / Trng |  | 80 | 1800 | 144 | plgd /1000 |  |  |  | 0 | 0 | 0
|  | 1507 | Controls Rep |  | 20 | 2000 | 40 | plgd /1000 | [5 empty] | 1507 | Controls Rep |  | 20 | 2000 | 40 | plgd /1000 |  |  |  | 0 | 0 | 0
|  | 1508 | DFO Treatment |  | 15 | 2000 | 30 | plgd /1000 | [5 empty] | 1508 | DFO Treatment |  | 15 | 2000 | 30 | plgd /1000 |  |  |  | 0 | 0 | 0
|  | 1509 | SCR |  | 0 | 2000 | 0 | plgd /1000 | [5 empty] | 1509 | SCR |  | 0 | 2000 | 0 | plgd /1000 |  |  |  | 0 | 0 | 0
[7 empty] | 541 |  | 541 | 541 | [8 empty] | 541 |  | 541 | 541 |  | 0 | 0 | 0
| 1600 Project Tests | [11 empty] | 1600 Project Tests
|  | 1601 | Soil Boring / Compaction |  |  |  | 20 | plgd /1000 | [5 empty] | 1601 | Soil Boring / Compaction |  |  |  | 20 | plgd /1000 |  |  |  | 0 | 0 | 0
|  | 1602 | Concrete |  |  |  | 40 | plgd /1000 | [5 empty] | 1602 | Concrete |  |  |  | 40 | plgd /1000 |  |  |  | 0 | 0 | 0
|  | 1603 | X Ray |  |  |  | 40 | plgd /1000 | [5 empty] | 1603 | X Ray |  |  |  | 40 | plgd /1000 |  |  |  | 0 | 0 | 0
|  | 1604 | Plant Performance and Reliability |  |  |  | 100 | plgd /1000 | [5 empty] | 1604 | Plant Performance and Reliability |  |  |  | 100 | plgd /1000 |  |  |  | 0 | 0 | 0
|  | 1605 | Emission Tests |  |  |  | 0 | plgd /1000 | [5 empty] | 1605 | Emission Tests |  |  |  | 0 | plgd /1000 |  |  |  | 0 | 0 | 0
|  | 1606 | Protective Relays |  |  |  | 20 | plgd /1000 | [5 empty] | 1606 | Protective Relays |  |  |  | 20 | plgd /1000 |  |  |  | 0 | 0 | 0
|  | 1607 | Acoustics / Noise Test |  |  |  | 0 | plgd /1000 | [5 empty] | 1607 | Acoustics / Noise Test |  |  |  | 0 | plgd /1000 |  |  |  | 0 | 0 | 0
[7 empty] | 220 |  | 220 | 220 | [8 empty] | 220 |  | 220 | 220 |  | 0 | 0 | 0
| 1700 Legal | [5 empty] | 0 | plgd /1000 | 0 |  |  |  | 1700 Legal | [5 empty] | 0 | plgd /1000 | 0 |  |  | 0 | 0 | 0
[24 empty] | 0 | 0 | 0
| 1800 Insurance / Securities | [11 empty] | 1800 Insurance / Securities
|  | 1810 | Bonds |  |  |  | 0 | plgd /1000 | [5 empty] | 1810 | Bonds |  |  |  | 0 | plgd /1000 |  |  |  | 0 | 0 | 0
|  | 1820 | Buildiers All Risk |  |  |  | 300 | plgd /1000 | [5 empty] | 1820 | Buildiers All Risk |  |  |  | 300 | plgd /1000 |  |  |  | 0 | 0 | 0
|  | 1830 | Marine / Cargo |  |  |  | 0 | plgd /1000 | [5 empty] | 1830 | Marine / Cargo |  |  |  | 0 | plgd /1000 |  |  |  | 0 | 0 | 0
|  | 1840 | Professional |  |  |  | 0 | plgd /1000 | [5 empty] | 1840 | Professional |  |  |  | 0 | plgd /1000 |  |  |  | 0 | 0 | 0
[7 empty] | 300 |  | 300 | 300 | [8 empty] | 300 |  | 300 | 300 |  | 0 | 0 | 0
| 1900 Taxes | [5 empty] | 0 | calc | 0 |  |  |  | 1900 Taxes | [5 empty] | 0 | calc | 0 |  |  | 0 | 0 | 0
[24 empty] | 0 | 0 | 0
| 2000 Commissions | [5 empty] | 0 | plgd /1000 | 0 |  |  |  | 2000 Commissions | [5 empty] | 0 | plgd /1000 | 0 |  |  | 0 | 0 | 0
[24 empty] | 0 | 0 | 0
| 2100 Project Contingency / Risk | [11 empty] | 2100 Project Contingency / Risk
|  | 2110 | Project Contingency |  |  |  | 1000 | plgd / 1000 |  | 1000 |  |  |  | 2110 | Project Contingency |  |  |  | 1000 | plgd / 1000 |  | 1000 |  | 0 | 0 | 0
|  | 2120 | GT Performance |  |  |  | 0 | plgd / 1000 | [5 empty] | 2120 | GT Performance |  |  |  | 0 | plgd / 1000 |  |  |  | 0 | 0 | 0
|  | 2130 | Schedule LD |  |  |  | 0 | plgd / 1000 | [5 empty] | 2130 | Schedule LD |  |  |  | 0 | plgd / 1000 |  |  |  | 0 | 0 | 0
|  | 2140 | Material Escalation |  | 0.05 | 8931.8 | 446.59 | calc |  | 446.59 |  |  |  | 2140 | Material Escalation |  | 0.05 | 9121.8 | 456.09 | calc |  | 456.09 |  | 9.5 | 9.5 | 0
|  | 2150 | Labor Contingency |  | 0.05 | 8121.2351 | 406.0618 | calc |  | 406.06 |  |  |  | 2150 | Labor Contingency |  | 0.05 | 8121.2351 | 406.0618 | calc |  | 406.06 |  | 0 | 0 | 0
[7 empty] | 1852.6518 |  | 1852.6518 | 1852.6518 | [8 empty] | 1862.1518 |  | 1862.1518 | 1862.1518 |  | 9.5 | 9.5 | 0
[5 empty] | BOP Cost |  |  |  | 29127.8569 | 20699.6037 | 71640.1523 | [5 empty] | BOP Cost |  |  |  | 34700.5358 | 22087.8984 | 107207.4178 | 5572.6789 | 1388.2947 | 35567.2654
[5 empty] | % Markup |  |  | 0.25 | 7281.9642 | 7281.9642 | 0 | [5 empty] | % Markup |  |  | 0.25 | 8675.1339 | 8675.1339 | 0 | 1393.1697 | 1393.1697 | 0
[5 empty] | BOP US$ Cost + Markup |  |  |  | 36409.8211 | [7 empty] | BOP US$ Cost + Markup |  |  |  | 43375.6697 |  |  | 6965.8486 | 2781.4644 | 35567.2654
[10 empty] | US$ | BsF | [10 empty] | US$ | BsF
[5 empty] | BOP Sales Price |  |  |  | 36409.8211 | 27981.5679 | 71640.1523 | [5 empty] | BOP Sales Price |  |  |  | 43375.6697 | 30763.0323 | 107207.4178 | 6965.8486 | 2781.4644 | 35567.2654
[5 empty] | Local Municipal & Social |  |  | 0.075 |  |  | 5373.0114 | [5 empty] | Local Municipal & Social |  |  | 0.075 |  |  | 8040.5563 |  |  | 2667.5449
[5 empty] | IVA |  |  | 0.16 |  |  | 11462.4244 | [5 empty] | IVA |  |  | 0.16 |  |  | 17153.1868 |  |  | 5690.7625
[5 empty] | Total BOP Sales Price Incl. Taxes |  |  |  |  | 27981.5679 | 88475.5881 | [5 empty] | Total BOP Sales Price Incl. Taxes |  |  |  |  | 30763.0323 | 132401.1609 |  | 2781.4644 | 43925.5728
[5 empty] | Proposed PES Price w/o Civil Scope |  |  | 29887944 | + | 97323146.957