## Plan
Planta la Raisa
Programa de Avance Físico : Ingenieria |  | Inicio: | 2009-12-14 |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
Cod. | Descripción | Unidad | Peso x Act | Durac. | Inicio | Fin | 2009-12-18 | 2009-12-25 | 2010-01-01 | 2010-01-08 | 2010-01-15 | 2010-01-22 | 2010-01-29 | 2010-02-05 | 2010-02-12 | 2010-02-19 | 2010-02-26 | 2010-03-05 | 2010-03-12 | 2010-03-19 | 2010-03-26 | 2010-04-02 | 2010-04-09 | 2010-04-16 | 2010-04-23 | 2010-04-30 | 2010-05-07 | 2010-05-14 | 2010-05-21 | 2010-05-28 | 2010-06-04 | 2010-06-11 | 2010-06-18 | 2010-06-25 | 2010-07-02 | 2010-07-09 | 2010-07-16 | 2010-07-23
1 | 30% Design Engineering 10, 20, 50, 60, 70 series prem drawings | 30 |  | 2 | 1 | 2
2 | COVER SHEET |  | 0.09 | 2 | 1 | 2 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
3 | MECHANICAL LEGENDS, SYMBOLS AND ABBREVIATIONS |  | 0.09 | 2 | 2 | 3 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
4 | ELECTRICAL LEGENDS, SYMBOLS AND ABBREVIATIONS |  | 0.09 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
5 | ELECTRICAL NOTES |  | 0.15 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
6 | ELECTRICAL ABBREVIATIONS |  | 0.09 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
7 | INSTRUMENTATION LEGENEDS, SYMBOLS AND ABBREVIATIONS |  | 0.09 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
8 | STRUCTURAL GENERAL NOTES |  | 0.15 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
9 | STANDARD CONCRETE DETAILS |  | 2.1 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
10 | GENERAL ARRANGEMENT PLOT PLAN-FT8-3 SWIFT PAC GTG UNITS |  | 0.3 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
11 | ROUGH GRADING PLAN |  | 2.4 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
12 | FOUNDATION LOCATION PLAN |  | 2.4 | 1 | 9 | 9 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
13 | FOUNDATION PLAN-FT8 GAS TURBINE GENERATOR GTG-100, GTG-200 |  | 2.4 |  | 9 |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
14 | FOUNDATION SECTIONS-FT8 GAS TURBINE GENERATOR GTG-100, GTG-200 |  | 2.4 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
15 | MAJOR EQUIP. ANCHOR BOLT PLAN-FT8 GAS TURBINE GENERATOR GTG-100, GTG-200 |  | 1.5 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
16 | FLOOR PITCH AND DRAIN PLAN-FT8 GAS TURBINE GENERATOR GTG-100, GTG-200 |  | 1.5 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
17 | JACKING PLATE/BAR LOCATION PLAN-FT8 GAS TURBINE GENERATOR GTG-100, GTG-200 |  | 1.5 | 1 | 9 | 9 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
18 | CONCRETE FINISH PLAN-FT8 GAS TURBINE GENERATOR GTG-100, GTG-200 |  | 1.5 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
19 | FOUNDATION REINFORCING BAR PLAN-FT8 GAS TURBINE GENERATOR GTG-100, GTG-200 |  | 1.5 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
20 | REINFORCING BAR SCHEDULE AND DETAILS-FT8 GAS TURBINE GENERATOR GTG-100, GTG-200 |  | 1.5 | 1 | 18 | 18 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
21 | PROCESS FLOW DIAGRAM-THREE (3) P & W FT8-3 SWIFT PAC UNITS |  | 0.15 | 2 | 18 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
22 | PROCESS FLOW DIAGRAM-THREE (3) P & W FT8-3 SWIFT PAC UNITS |  | 0.15 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
23 | PROCESS FLOW DIAGRAM-THREE (3) P & W FT8-3 SWIFT PAC UNITS |  | 0.15 | 1 | 18 | 18 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
24 | PROCESS FLOW DIAGRAM-THREE (3) P & W FT8-3 SWIFT PAC UNITS |  | 0.15 | 2 | 1 | 2 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
25 | MECHANICAL EQUIPMENT LIST |  | 0.15 | 2 | 1 | 2 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
28 | WATER BALANCE |  | 0.3 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
29 | ONE LINE DIAGRAM-FT8-3 SWIFT PAC 50, FT8-3 POWER PAK 25 & STG UNITS |  | 0.15 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
30 | ONE LINE DIAGRAM-T2 & MCC-WATER/FUEL |  | 0.15 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
31 | ONE LINE DIAGRAM-LV MCC-COMP |  | 0.15 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
32 | ONE LINE DIAGRAM-MCC-HV |  | 0.15 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
33 | GTG-100 ONE LINE-FT8-3 SWIFT PAC |  | 0.15 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
34 | MCC ACD2, DCD1 & DCD2-GTG-100 ONE LINE DIAGRAMS |  | 0.15 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
35 | MCC STARTERS & CONTACTORS-GTG-100 |  | 0.15 | 1 | 9 | 9 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
36 | BREAKER PANELS ACD1 & ACD1G-GTG-100 |  | 0.15 |  | 9 |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
37 | BREAKER PANELS ACD1A & ACD1B-GTG-100 |  | 0.15 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
38 | GTG-100 THREE LINE FT8-3 SWIFT PAC |  | 0.15 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
39 | GTG-200 ONE LINE-FT8-3 SWIFT PAC |  | 0.15 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
40 | MCC ACD2, DCD1 & DCD2-GTG-200 ONE LINE DIAGRAMS |  | 0.15 | 1 | 9 | 9 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
41 | MCC STARTERS & CONTACTORS-GTG-200 |  | 0.15 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
42 | BREAKER PANELS ACD1 & ACD1G-GTG-200 |  | 0.15 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
43 | BREAKER PANELS ACD1A & ACD1B-GTG-200 |  | 0.15 | 1 | 18 | 18 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
44 | GTG-200 THREE LINE FT8-3 SWIFT PAC |  | 0.15 | 2 | 18 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
45 | GTG-300 ONE LINE-FT8-3 SWIFT PAC |  | 0.15 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
46 | MCC ACD2, DCD1 & DCD2-GTG-300 ONE LINE DIAGRAMS |  | 0.15 | 1 | 18 | 18 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
47 | MCC STARTERS & CONTACTORS-GTG-300 |  | 0.15 | 2 | 1 | 2 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
48 | BREAKER PANELS ACD1 & ACD1G-GTG-300 |  | 0.15 | 2 | 1 | 2 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
49 | BREAKER PANELS ACD1A & ACD1B-GTG-300 |  | 0.15 | 2 | 2 | 3 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
50 | GTG-300 THREE LINE-FT8-3 SWIFT PAC |  | 0.15 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
51 | ONE LINE DIAGRAM LEGEND GTG-100, 200 & 300 |  | 0.09 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
52 | PROT. RELAY & LOCKOUT RELAY TRIP SCHEDULE-GTG-100, 200 & 300 |  | 0.15 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
53 | 86 LOCKOUT/TRIPPING RELAY SCHEDULE-GTG-100, 200 & 300 |  | 0.15 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
54 | EQUIPMENT DRAWING-GSU RELAY PANEL RP-100/200/300 |  | 0.15 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
55 | EQUIPMENT DRAWING-GSU RELAY PANEL RP-100/200/300 |  | 0.15 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
56 | EQUIPMENT DRAWING-GSU RELAY PANEL RP-100/200/300 |  | 0.15 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
57 | EQUIPMENT DRAWING-GSU RELAY PANEL RP-100/200/300 |  | 0.15 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
58 | EQUIPMENT DRAWING-DCS ENCLOSURE CABINET 1 |  | 0.15 | 1 | 9 | 9 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
59 | EQUIPMENT DRAWING-DCS TERMINATION CABINET 1 |  | 0.15 |  | 9 |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
60 | EQUIPMENT DRAWING-DCS ENCLOSURE CABINET 2 |  | 0.15 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
61 | EQUIPMENT DRAWING-DCS TERMINATION CABINET 2 |  | 0.15 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
62 | EQUIPMENT DRAWING-DCS ENCLOSURE CABINET 3 |  | 0.15 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
63 | EQUIPMENT DRAWING-DCS TERMINATION CABINET 3 |  | 0.15 | 1 | 9 | 9 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
64 | EQUIPMENT DRAWING-FIBER OPTIC PANEL 1, MCC ROOM |  | 0.15 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
65 | EQUIPMENT DRAWING-TYPICAL FIBER OPTIC PANEL |  | 0.15 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
66 | CONTROL SCHEMATIC-GSU RP-100 87T1, 86T1A&B |  | 0.15 | 1 | 18 | 18 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
67 | CONTROL SCHEMATIC-GSU RP-200 87T2, 86T2A&B |  | 0.15 | 2 | 18 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
68 | CONTROL SCHEMATIC-GSU RP-300 87T3, 86T3A&B |  | 0.15 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
69 | ELECTRICAL EQUIPMENT LIST |  | 0.09 | 1 | 18 | 18 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
70 | ELECTRICAL EQUIPMENT LIST |  | 0.09 | 2 | 1 | 2 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
71 | DCS ARCHITECTURE |  | 0.09 | 2 | 1 | 2 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
72 | ESD-2002 LOGIC FLOW DIAGRAM |  | 0.15 | 2 | 2 | 3 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
73 | P-1401A/B-LOGIC FLOW DIAGRAM |  | 0.15 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
74 | P-1402A/B-LOGIC FLOW DIAGRAM |  | 0.15 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
75 | P-1410A/B-LOGIC FLOW DIAGRAM |  | 0.15 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
76 | P-1430A/B-LOGIC FLOW DIAGRAM |  | 0.15 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
77 | P-1501A/B-LOGIC FLOW DIAGRAM |  | 0.15 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
78 | P-1530A/B/C-LOGIC FLOW DIAGRAM |  | 0.09 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
80 | 60% Design engineering 10, 20, 30, 50, 60, 70 series drawings | 30 | 0 | 2 | 9 | 10 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 0
81 | Index 60 % |  | 30 | 1 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 70 | 85 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
82 | 90% Design Engineering 10, 20, 30, 40, 50, 60, 70 series drawings | 30 |  |  | 9 | bar: 1 to 8; 14 to 17; 19 to 32
83 | Index 90 % |  | 30 | 2 | 9 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 20 | 20 | 20 | 20 | 70 | 85 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
84 | Issue for Construction Drawings |  | 10 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
|  |  | 100 |  |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 29 | 33.5 | 38 | 38 | 38 | 53 | 57.5 | 62 | 68 | 68 | 68 | 68 | 83 | 87.5 | 89 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100

## Real Ing
Planta la Raisa
Programa de Avance Físico : Ingenieria |  | Inicio: | 2009-12-14 |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32
Cod. | Descripción | Unidad | Peso x Act | Durac. | Inicio | Fin | 2009-12-18 | 2009-12-25 | 2010-01-01 | 2010-01-08 | 2010-01-15 | 2010-01-22 | 2010-01-29 | 2010-02-05 | 2010-02-12 | 2010-02-19 | 2010-02-26 | 2010-03-05 | 2010-03-12 | 2010-03-19 | 2010-03-26 | 2010-04-02 | 2010-04-09 | 2010-04-16 | 2010-04-23 | 2010-04-30 | 2010-05-07 | 2010-05-14 | 2010-05-21 | 2010-05-28 | 2010-06-04 | 2010-06-11 | 2010-06-18 | 2010-06-25 | 2010-07-02 | 2010-07-09 | 2010-07-16 | 2010-07-23
1 | 30% Design Engineering 10, 20, 50, 60, 70 series prem drawings | 30 |  | 2 | 1 | 2
2 | COVER SHEET | 0 | 0.07 | 2 | 1 | 2 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
3 | MECHANICAL LEGENDS, SYMBOLS AND ABBREVIATIONS | 0 | 0.07 | 2 | 2 | 3 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
4 | ELECTRICAL LEGENDS, SYMBOLS AND ABBREVIATIONS | 0 | 0.07 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
5 | ELECTRICAL NOTES | 0 | 0.07 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
6 | ELECTRICAL ABBREVIATIONS | 0 | 0.07 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
7 | INSTRUMENTATION LEGENEDS, SYMBOLS AND ABBREVIATIONS | 0 | 0.07 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 90 | 90 | 90 | 90
8 | STRUCTURAL GENERAL NOTES | 0 | 0.07 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
9 | STANDARD CONCRETE DETAILS | 0 | 1.20 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
10 | GENERAL ARRANGEMENT PLOT PLAN-FT8-3 SWIFT PAC GTG UNITS | 0 | 0.2 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
11 | ROUGH GRADING PLAN | 0 | 1 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 95 | 95 | 95 | 95 | 95 | 95 | 100 | 100 | 100 | 100
12 | FOUNDATION LOCATION PLAN | 0 | 1 | 1 | 9 | 9 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
13 | FOUNDATION PLAN-FT8 GAS TURBINE GENERATOR GTG-100, GTG-200 | 0 | 1.2 |  | 9 |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
14 | FOUNDATION SECTIONS-FT8 GAS TURBINE GENERATOR GTG-100, GTG-200 | 0 | 1.2 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
15 | MAJOR EQUIP. ANCHOR BOLT PLAN-FT8 GAS TURBINE GENERATOR GTG-100, GTG-200 | 0 | 1 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
16 | FLOOR PITCH AND DRAIN PLAN-FT8 GAS TURBINE GENERATOR GTG-100, GTG-200 | 0 | 1 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
17 | JACKING PLATE/BAR LOCATION PLAN-FT8 GAS TURBINE GENERATOR GTG-100, GTG-200 | 0 | 1 | 1 | 9 | 9 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 100 | 100 | 100 | 100
18 | CONCRETE FINISH PLAN-FT8 GAS TURBINE GENERATOR GTG-100, GTG-200 | 0 | 1.2 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
19 | FOUNDATION REINFORCING BAR PLAN-FT8 GAS TURBINE GENERATOR GTG-100, GTG-200 | 0 | 1 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
20 | REINFORCING BAR SCHEDULE AND DETAILS-FT8 GAS TURBINE GENERATOR GTG-100, GTG-200 | 0 | 1 | 1 | 18 | 18 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
21 | PROCESS FLOW DIAGRAM-THREE (3) P & W FT8-3 SWIFT PAC UNITS | 0 | 0.07 | 2 | 18 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
22 | PROCESS FLOW DIAGRAM-THREE (3) P & W FT8-3 SWIFT PAC UNITS | 0 | 0.07 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
23 | PROCESS FLOW DIAGRAM-THREE (3) P & W FT8-3 SWIFT PAC UNITS | 0 | 0.07 | 1 | 18 | 18 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
24 | PROCESS FLOW DIAGRAM-THREE (3) P & W FT8-3 SWIFT PAC UNITS | 0 | 0.07 | 2 | 1 | 2 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
25 | MECHANICAL EQUIPMENT LIST | 0 | 0.07 | 2 | 1 | 2 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
28 | WATER BALANCE | 0 | 0.3 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
29 | ONE LINE DIAGRAM-FT8-3 SWIFT PAC 50, FT8-3 POWER PAK 25 & STG UNITS | 0 | 0.07 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
30 | ONE LINE DIAGRAM-T2 & MCC-WATER/FUEL | 0 | 0.07 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
31 | ONE LINE DIAGRAM-LV MCC-COMP | 0 | 0.07 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
32 | ONE LINE DIAGRAM-MCC-HV | 0 | 0.07 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
33 | GTG-100 ONE LINE-FT8-3 SWIFT PAC | 0 | 0.07 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
34 | MCC ACD2, DCD1 & DCD2-GTG-100 ONE LINE DIAGRAMS | 0 | 0.07 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
35 | MCC STARTERS & CONTACTORS-GTG-100 | 0 | 0.07 | 1 | 9 | 9 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
36 | BREAKER PANELS ACD1 & ACD1G-GTG-100 | 0 | 0.07 |  | 9 |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
37 | BREAKER PANELS ACD1A & ACD1B-GTG-100 | 0 | 0.07 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
38 | GTG-100 THREE LINE FT8-3 SWIFT PAC | 0 | 0.07 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
39 | GTG-200 ONE LINE-FT8-3 SWIFT PAC | 0 | 0.07 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
40 | MCC ACD2, DCD1 & DCD2-GTG-200 ONE LINE DIAGRAMS | 0 | 0.07 | 1 | 9 | 9 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
41 | MCC STARTERS & CONTACTORS-GTG-200 | 0 | 0.07 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
42 | BREAKER PANELS ACD1 & ACD1G-GTG-200 | 0 | 0.07 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
43 | BREAKER PANELS ACD1A & ACD1B-GTG-200 | 0 | 0.07 | 1 | 18 | 18 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
44 | GTG-200 THREE LINE FT8-3 SWIFT PAC | 0 | 0.07 | 2 | 18 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
45 | GTG-300 ONE LINE-FT8-3 SWIFT PAC | 0 | 0.07 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
46 | MCC ACD2, DCD1 & DCD2-GTG-300 ONE LINE DIAGRAMS | 0 | 0.07 | 1 | 18 | 18 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
47 | MCC STARTERS & CONTACTORS-GTG-300 | 0 | 0.07 | 2 | 1 | 2 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
48 | BREAKER PANELS ACD1 & ACD1G-GTG-300 | 0 | 0.07 | 2 | 1 | 2 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
49 | BREAKER PANELS ACD1A & ACD1B-GTG-300 | 0 | 0.07 | 2 | 2 | 3 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
50 | GTG-300 THREE LINE-FT8-3 SWIFT PAC | 0 | 0.07 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
51 | ONE LINE DIAGRAM LEGEND GTG-100, 200 & 300 | 0 | 0.07 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
52 | PROT. RELAY & LOCKOUT RELAY TRIP SCHEDULE-GTG-100, 200 & 300 | 0 | 0.07 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
53 | 86 LOCKOUT/TRIPPING RELAY SCHEDULE-GTG-100, 200 & 300 | 0 | 0.07 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
54 | EQUIPMENT DRAWING-GSU RELAY PANEL RP-100/200/300 | 0 | 0.07 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 90 | 90 | 90 | 90
55 | EQUIPMENT DRAWING-GSU RELAY PANEL RP-100/200/300 | 0 | 0.07 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 90 | 90 | 90 | 90
56 | EQUIPMENT DRAWING-GSU RELAY PANEL RP-100/200/300 | 0 | 0.07 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
57 | EQUIPMENT DRAWING-GSU RELAY PANEL RP-100/200/300 | 0 | 0.07 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
58 | EQUIPMENT DRAWING-DCS ENCLOSURE CABINET 1 | 0 | 0.07 | 1 | 9 | 9 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
59 | EQUIPMENT DRAWING-DCS TERMINATION CABINET 1 | 0 | 0.07 |  | 9 |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 90 | 90 | 90 | 90
60 | EQUIPMENT DRAWING-DCS ENCLOSURE CABINET 2 | 0 | 0.07 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
61 | EQUIPMENT DRAWING-DCS TERMINATION CABINET 2 | 0 | 0.07 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
62 | EQUIPMENT DRAWING-DCS ENCLOSURE CABINET 3 | 0 | 0.07 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
63 | EQUIPMENT DRAWING-DCS TERMINATION CABINET 3 | 0 | 0.07 | 1 | 9 | 9 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 90 | 90 | 90 | 90
64 | EQUIPMENT DRAWING-FIBER OPTIC PANEL 1, MCC ROOM | 0 | 0.07 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
65 | EQUIPMENT DRAWING-TYPICAL FIBER OPTIC PANEL | 0 | 0.07 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90 | 90
66 | CONTROL SCHEMATIC-GSU RP-100 87T1, 86T1A&B | 0 | 0.07 | 1 | 18 | 18 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 90 | 90 | 90 | 90
67 | CONTROL SCHEMATIC-GSU RP-200 87T2, 86T2A&B | 0 | 0.07 | 2 | 18 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 90 | 90 | 90 | 90
68 | CONTROL SCHEMATIC-GSU RP-300 87T3, 86T3A&B | 0 | 0.07 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 90 | 90 | 90 | 90
69 | ELECTRICAL EQUIPMENT LIST | 0 | 0.07 | 1 | 18 | 18 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 90 | 90 | 90 | 90
70 | ELECTRICAL EQUIPMENT LIST | 0 | 0.07 | 2 | 1 | 2 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80
71 | DCS ARCHITECTURE | 0 | 0.07 | 2 | 1 | 2 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 90 | 90 | 90 | 90
72 | ESD-2002 LOGIC FLOW DIAGRAM | 0 | 0.07 | 2 | 2 | 3 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 90 | 90 | 90 | 90
73 | P-1401A/B-LOGIC FLOW DIAGRAM | 0 | 0.07 |  |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 90 | 90 | 90 | 90
74 | P-1402A/B-LOGIC FLOW DIAGRAM | 0 | 0.07 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 90 | 90 | 90 | 90
75 | P-1410A/B-LOGIC FLOW DIAGRAM | 0 | 0.07 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 90 | 90 | 90 | 90
76 | P-1430A/B-LOGIC FLOW DIAGRAM | 0 | 0.07 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 90 | 90 | 90 | 90
77 | P-1501A/B-LOGIC FLOW DIAGRAM | 0 | 0.07 | 13 | 7 | 19 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 90 | 90 | 90 | 90
78 | P-1530A/B/C-LOGIC FLOW DIAGRAM | 0 | 0.07 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 70 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 80 | 90 | 90 | 90 | 90
79 | 60% Design engineering 10, 20, 30, 50, 60, 70 series drawings | 30 | 0 | 2 | 9 | 10 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 0
81 | Index 60 % | 0 |  | 1 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 20 | 20 | 20 | 20 | 60 | 20 | 70 | 70 | 70 | 70 | 70 | 70 | 70
82 | FOUNDATION PLAN AND DETAILS-GROUNDING STUB UPS |  | 1.2 |  |  |  | 14: 70; 15: 100; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
83 | FOUNDATION PLAN AND SECTIONS RAW LIQUID FUEL TANK |  | 1.2 |  |  |  | 14: 70; 15: 100; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
84 | FOUNDATION PLAN AND SECTIONS DEMIN WATER TANK |  | 1.2 |  |  |  | 14: 70; 15: 100; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
85 | FOUNDATION PLAN AND SECTIONS CLEAN LIQUID FUEL TANK |  | 1.2 |  |  |  | 14: 70; 15: 100; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
86 | FOUNDATION PLAN AND SECTIONS RAW / FIRE WATER TANK |  | 1.2 |  |  |  | 14: 70; 15: 100; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| FOUNDATION PLAN GSU |  | 1.2 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| FOUNDATION SECTIONS GSU |  | 1.2 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| SLAB REINFORCING GSU |  | 0.07 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| REINFORCING BAR SCHEDULE AND DETAILS GSU |  | 0.07 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| FOUNDATION PLAN AND SECTIONS GAS COMPRESSORS FIN FANS |  | 1.2 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| FOUNDATION PLAN AND SECTIONS OILY WATER SEPARATOR |  | 1.2 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| REINFORCING PLAN AND SCHEDULE OILY WATER SEPARATOR |  | 0.07 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| FOUNDATION PLAN AND SECTIONS GAS FUEL FILTER REGULATOR |  | 1.2 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| FOUNDATION PLAN AND SECTIONS WASTE OIL TANK |  | 1.2 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| FOUNDATION PLAN AND SECTIONS EMERGENCY GENERATOR |  | 1.2 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| FOUNDATION PLAN AND SECTIONS WASTE OIL SUMP WITH PUMP |  | 1.2 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| REINFORCING BAR PLAN AND SCHEDULE WASTE OIL SUMP WITH PUMP |  | 0.07 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| FOUNDATION PLAN AND SECTIONS LIQUID FUEL OFFLOAD |  | 1.2 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| REINFORCING BAR PLAN AND SCHEDULE LIQUID FUEL OFFLOAD |  | 0.07 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| FOUNDATION PLAN AND SECTIONS AUX TRANSFORMERS |  | 1.2 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| REINFORCING BAR AND SCHEDULE AUX TRANSFORMERS |  | 0.07 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| FOUNDATION PLAN AND SECTIONS SUMP PIT |  | 1.15 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| FOUNDATION LOCATION PLAN PIPE SUPPORTS FOUNDATIONS |  | 1.16 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| FOUNDATION PLAN AND SECTIONS PIPE SUPPORTS FOUNDATIONS |  | 1.17 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| FOUNDATION PLAN AND SECTIONS R.O. TANK |  | 1.17 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| BUILDING FOUNDATION PLANS AND DETAILS GENERAL STRUCTURAL DATA |  | 0.07 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| BUILDING FOUNDATION PLANS AND DETAILS OFFICE BUILDING |  | 0.07 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| BUILDING FOUNDATION PLANS AND DETAILS ELECTRICAL BUILDING |  | 0.07 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| BUILDING FOUNDATION PLANS AND DETAILS CONTROL BUILDING |  | 0.07 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| BUILDING FOUNDATION PLANS AND DETAILS WATER TREATMENT BUILDING |  | 0.07 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| BUILDING FOUNDATION PLANS AND DETAILS GAS COMPRESSOR BLDG / FIRE WATER SHED |  | 0.07 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| BUILDING FOUNDATION PLANS AND DETAILS LIQUID FOAM SHED / FOAM GENERATION BLDG |  | 0.07 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| BUILDING FOUNDATION DETAILS |  | 0.07 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| BUILDING FOUNDATION DETAILS |  | 0.07 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| BUILDING FOUNDATION DETAILS |  | 0.07 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| T-1000 RAW LIQUID FUEL STORAGE TANK - DETAILS |  | 0.07 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| T-1000 RAW LIQUID FUEL STORAGE TANK - TOMBSTONE REPAD DETAILS |  | 0.07 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| T-1001 RAW LIQUID FUEL STORAGE TANK - DETAILS |  | 0.07 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| T-1001 RAW LIQUID FUEL STORAGE TANK - TOMBSTONE REPAD DETAILS |  | 0.07 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| T-1002 CLEAN LIQUID FUEL STORAGE TANK - SAFETY GATE DETAILS |  | 0.07 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| T-1002 CLEAN LIQUID FUEL STORAGE TANK - TOMBSTONE REPAD DETAILS |  | 0.07 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| T-1003 CLEAN LIQUID FUEL STORAGE TANK - SAFETY GATE DETAILS |  | 0.07 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| T-1003 CLEAN LIQUID FUEL STORAGE TANK - TOMBSTONE REPAD DETAILS |  | 0.07 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| T-1005 CLARIFIED WATER / FIRE WATER TANK - MANWAYS |  | 0.07 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| T-1006 DEMINERALIZED WATER STORAGE TANK - SAFETY GATE DETAIL |  | 0.07 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
| T-1006 DEMINERALIZED WATER STORAGE TANK - TOMBSTONE REPAD DETAILS |  | 0.07 |  |  |  | 15: 70; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
87 | FLOOR PLAN-OFFICE BUILDING |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 90; 18: 90; 19: 90; 20: 90
88 | LIGHTING PLAN-OFFICE BUILDING |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 90
89 | FLOOR PLAN-ELECTRICAL BUILDING |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 90; 18: 90; 19: 90; 20: 90
90 | LIGHTING PLAN-UTILITY BUILDING |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 90
91 | FLOOR PLAN-CONTROL BUILDING |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 90; 18: 90; 19: 90; 20: 90
92 | LIGHTING PLAN-CONTROL BUILDING |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 90
93 | FLOOR PLAN-WATER TREATMENT BUILDING |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 90; 18: 90; 19: 90; 20: 90
94 | LIGHTING PLAN-WATER TREATMENT BUILDING |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 90
95 | FLOOR PLAN-GAS COMPRESSOR BUILDING |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 90; 18: 90; 19: 90; 20: 90
96 | LIGHTING PLAN-GAS COMPRESSOR BUILDING |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 90
97 | FLOOR PLAN-FIRE WATER SHED |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 90; 18: 90; 19: 90; 20: 90
98 | LIGHTING PLAN-FIRE WATER SHED |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 90
99 | FLOOR PLAN-LIQUID FUEL TREATMENT SHED |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 90; 18: 90; 19: 90; 20: 90
100 | LIGTHING PLAN-LIQUID FUEL TREATMENT SHED |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 90
101 | FLOOR PLAN-FOAM GENERATING BUILDING |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 90; 18: 90; 19: 90; 20: 90
102 | LIGHTING PLAN-FOAM GENERATING BUILDING |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 90
103 | FLOOR PLAN-DIESEL OF LOADING SHED |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 90; 18: 90; 19: 90; 20: 90
104 | ESTRUCTURAL STEEL PLAN AND ELEV-CABLE TRY SUPPORTS |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 80
105 | ESTRUCTURAL STEEL PLAN AND ELEV-CABLE TRY SUPPORTS |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 80
106 | ESTRUCTURAL STEEL DETAIL-CABLE TRY SUPPORTS |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 80
107 | TYPICAL PIPE SUPPORTS |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 80
108 | TYPICAL PIPE SUPPORTS |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 80
109 | TYPICAL PIPE SUPPORTS |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 80
110 | TYPICAL PIPE SUPPORTS |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 80
111 | PROCESS & INSTRUMENT DIAGRAM-GTG 100 TURBINE CONNECTION |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 80
112 | PROCESS & INSTRUMENT DIAGRAM-GTG 100-LIQUID FUEL AUX SKID CONNECTION |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 80
113 | PROCESS & INSTRUMENT DIAGRAM-GTG 100- DEMIN WATER AUX SKID CONNECTION |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 80
114 | PROCESS & INSTRUMENT DIAGRAM-GTG 200 TURBINE CONNECTION |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 80
115 | PROCESS & INSTRUMENT DIAGRAM-GTG 200-LIQUID FUEL AUX SKID CONNECTION |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 80
116 | PROCESS & INSTRUMENT DIAGRAM-GTG 200- DEMIN WATER AUX SID CONNECTION |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 80
117 | PROCESS & INSTRUMENT DIAGRAM-GTG 300 TURBINE CONNECTION |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 80
118 | PROCESS & INSTRUMENT DIAGRAM-GTG 300-LIQUID FUEL AUX SKID CONNECTION |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
119 | PROCESS & INSTRUMENT DIAGRAM-GTG 300- DEMIN WATER AUX SID CONNECTION |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
120 | PROCESS & INSTRUMENT DIAGRAM-NATURAL GAS SYSTEM |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 90; 20: 90
121 | PROCESS & INSTRUMENT DIAGRAM-NATURAL GAS SYSTEM |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 90; 20: 90
122 | PROCESS & INSTRUMENT DIAGRAM-NATURAL GAS SYSTEM |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 90; 20: 90
123 | PROCESS & INSTRUMENT DIAGRAM-LIQUID FUEL SYSTEM |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 90; 20: 90
124 | PROCESS & INSTRUMENT DIAGRAM-LIQUID FUEL SYSTEM |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 90; 20: 90
125 | PROCESS & INSTRUMENT DIAGRAM-LIQUID FUEL SYSTEM |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 90; 20: 90
126 | PROCESS & INSTRUMENT DIAGRAM-LIQUID FUEL SYSTEM |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 90; 20: 90
127 | PROCESS & INSTRUMENT DIAGRAM-LIQUID FUEL SYSTEM |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 90; 20: 90
128 | PROCESS & INSTRUMENT DIAGRAM-LIQUID FUEL SYSTEM |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 90; 20: 90
129 | PROCESS & INSTRUMENT DIAGRAM-LIQUID FUEL SYSTEM |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 90; 20: 90
130 | PROCESS & INSTRUMENT DIAGRAM-LIQUID FUEL SYSTEM |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 90; 20: 90
131 | PROCESS & INSTRUMENT DIAGRAM-LIQUID FUEL SYSTEM |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 90; 20: 90
132 | PROCESS & INSTRUMENT DIAGRAM-LIQUID FUEL SYSTEM |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 90; 20: 90
133 | PROCESS & INSTRUMENT DIAGRAM-RAW WATER SYSTEM |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 90; 20: 90
134 | PROCESS & INSTRUMENT DIAGRAM-RAW WATER SYSTEM |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 90; 20: 90
135 | PROCESS & INSTRUMENT DIAGRAM-DEMIN WATER SYSTEM |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 90; 20: 90
136 | PROCESS & INSTRUMENT DIAGRAM-DEMIN WATER SYSTEM |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 90; 20: 90
137 | PROCESS & INSTRUMENT DIAGRAM-DEMIN WATER SYSTEM |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 90; 20: 90
138 | PROCESS & INSTRUMENT DIAGRAM-DEMIN WATER SYSTEM |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 90; 20: 90
139 | PROCESS & INSTRUMENT DIAGRAM-TURBINE WATER WASH SKIDS |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 90; 20: 90
140 | PROCESS & INSTRUMENT DIAGRAM-INSTRUMENT AIR SYSTEMS |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 90; 20: 90
141 | PROCESS & INSTRUMENT DIAGRAM-INSTRUMENT AIR SYSTEMS |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 90; 20: 90
142 | PROCESS & INSTRUMENT DIAGRAM-INSTRUMENT AIR SYSTEMS |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 90; 20: 90
143 | PROCESS & INSTRUMENT DIAGRAM-DRAIN SYSTEMS |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 90; 20: 90
144 | PROCESS & INSTRUMENT DIAGRAM-DRAIN SYSTEMS |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 90; 20: 90
145 | PROCESS & INSTRUMENT DIAGRAM-DRAIN SYSTEMS |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 90; 20: 90
146 | PIPING LOCATION PLOT PLAN-FT8-3 SWIFT PAC GTG UNITS |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
147 | ONE LINE DIAGRAM-EMERGENCY GENERATOR ONE LINE |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
148 | ONE LINE DIAGRAM LEGEND GTG-100, 200 & 300 |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 80
149 | PROT. RELAY & LOCKOUT RELAY TRIP SCHEDULE-GTG-100, 200 & 300 |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 80
150 | 86 LOCKOUT/TRIPPING RELAY SCHEDULE-GTG-100, 200 & 300 |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 80
151 | GTG-100 SCHEMATIC-GENERATOR THREE LINE |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
152 | GTG-100 SCHEMATIC-GENERATOR THREE LINE |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
153 | GTG-100 SCHEMATIC-GENERATOR THREE LINE |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
154 | GTG-100 SCHEMATIC-GENERATOR THREE LINE |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
155 | GTG-100 SCHEMATIC-GENERATOR THREE LINE |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
156 | GTG-100 SCHEMATIC-GENERATOR THREE LINE |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
157 | GTG-100 SCHEMATIC-GENERATOR THREE LINE |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
158 | GTG-200 SCHEMATIC-GENERATOR THREE LINE |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
159 | GTG-200 SCHEMATIC-GENERATOR THREE LINE |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
160 | GTG-200 SCHEMATIC-GENERATOR THREE LINE |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
161 | GTG-200 SCHEMATIC-GENERATOR THREE LINE |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
162 | GTG-200 SCHEMATIC-GENERATOR THREE LINE |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
163 | GTG-200 SCHEMATIC-GENERATOR THREE LINE |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
164 | GTG-200 SCHEMATIC-GENERATOR THREE LINE |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
165 | GTG-300 SCHEMATIC-GENERATOR THREE LINE |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
166 | GTG-300 SCHEMATIC-GENERATOR THREE LINE |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
167 | GTG-300 SCHEMATIC-GENERATOR THREE LINE |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
168 | GTG-300 SCHEMATIC-GENERATOR THREE LINE |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
169 | GTG-300 SCHEMATIC-GENERATOR THREE LINE |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
170 | GTG-300 SCHEMATIC-GENERATOR THREE LINE |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
171 | GTG-300 SCHEMATIC-GENERATOR THREE LINE |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
172 | THREE LINE DIAGRAM-FT8-3 SWIFT PAC 50 SWGR-400 |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
173 | THREE LINE DIAGRAM-FT8-3 SWIFT PAC 50 SWGR-500 |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
174 | EQUIPMENT DRAWING-SYN CONTROL PANEL SP-100 |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 80
175 | EQUIPMENT DRAWING-OUTSIDE AREA LGHTG PANEL LP-2A |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 90; 18: 90; 19: 90; 20: 90
176 | EQUIPMENT DRAWING-ESD PANEL 1 |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 90; 17: 80; 18: 80; 19: 80; 20: 80
177 | EQUIPMENT DRAWINGS-ESD PANEL 1 THRU 5 |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 80
178 | EQUIPMENT DRAWINGS-15 KV CABLE TRAY LAYOUT & DETAILS |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 80
179 | EQUIPMENT DRAWINGS-P & W FT-8 15KV CABLE ENTRANCE |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 70; 17: 80; 18: 80; 19: 80; 20: 80
180 | CONTROL SCHEMATIC GSU RP 200 87T2, 86T2 A& B |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 90; 18: 90; 19: 90; 20: 90
181 | CONTROL SCHEMATIC GSU RP 300 87T2, 86T2 A& B |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 90; 18: 90; 19: 90; 20: 90
182 | CONTROL SCHEMATIC GSU RP 300 87T2, 86T2 A& B |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 90; 18: 90; 19: 90; 20: 90
183 | CONTROL SCHEMATIC-400V LIGHTING EQUIPMENT LP-1 |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
184 | CONTROL SCHEMATIC-ESD & RAW WATER SOV |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
185 | SCHEMATIC-DIAGRAM-SWGR-400 52-1 CONTROL |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
186 | SCHEMATIC-DIAGRAM-SWGR-400 52-2 CONTROL |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
187 | SCHEMATIC-DIAGRAM-SWGR-400 52-3 CONTROL |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
188 | SCHEMATIC-DIAGRAM-SWGR-400 52-A CONTROL |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
189 | SCHEMATIC-DIAGRAM-SWGR-400 52-B CONTROL |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
190 | SCHEMATIC-DIAGRAM-SWGR-500 52-A CONTROL |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
191 | SCHEMATIC-DIAGRAM-SWGR-500 52-B CONTROL |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
192 | SCHEMATIC-DIAGRAM-SWGR-500 52-1 CONTROL |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
193 | SCHEMATIC-DIAGRAM-SWGR-500 52-2 CONTROL |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
194 | SCHEMATIC-DIAGRAM-SWGR-500 52-3 CONTROL |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
195 | SCHEMATIC-DIAGRAM-SWGR-500 52-4 CONTROL |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
196 | SCHEMATIC-DIAGRAM-SWGR-500 52-5 CONTROL |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
197 | CONTROL SCHEMATIC-152 SF6 CIRCUIT BREAKER |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
198 | SCHEMATICS-TYPICAL MCC CONTROL SCHEMATIC |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
199 | SCHEMATICS-GAS COMPRESSOR C-130A & C-130B |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
200 | SCHEMATICS-GAS COMPRESSOR C-130C |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
201 | ELECTRICAL CABLE DETAILS |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
202 | ELECTRICAL GROUNDING DETAILS |  | 0.07 |  |  |  | 14: 70; 15: 100; 16: 100; 17: 100; 18: 100; 19: 100; 20: 100
203 | INTERCONNECT DIAGRAM-MCC-WATER/FUEL |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
204 | INTERCONNECT DIAGRAM-MCC-WATER/FUEL |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
205 | INTERCONNECT DIAGRAM-MCC-WATER/FUEL |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
206 | INTERCONNECT DIAGRAM-MCC-WATER/FUEL |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
207 | INTERCONNECT DIAGRAM-MCC-WATER/FUEL |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
208 | INTERCONNECT DIAGRAM-MCC-COMP |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
209 | INTERCONNECT DIAGRAM-MCC-COMP |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
210 | INTERCONNECT DIAGRAM-MCC-COMP |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
211 | INTERCONNECT DIAGRAM-MCC-HV |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
212 | ELECTRICAL LOCATION PLOT PLAN-FT8-3 SWIFT PAC GTG UNITS |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
213 | AREA CLASSIFICATION |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
214 | AREA LIGHTING |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
215 | TYPICAL MANHOLE DETAILS |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
216 | MANHOLE DETAILS |  | 0.07 |  |  |  | 14: 70; 15: 90; 16: 80; 17: 90; 18: 90; 19: 90; 20: 90
217 | MANHOLE DETAILS |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 90; 18: 90; 19: 90; 20: 90
218 | MANHOLE DETAILS |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
219 | MANHOLE DETAILS |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
220 | ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 14: 70; 15: 90; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
221 | ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 14: 70; 15: 90; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
222 | ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 14: 70; 15: 90; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
223 | ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 14: 70; 15: 90; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
224 | GROUNDING PLOT PLAN |  | 0.07 |  |  |  | 14: 70; 15: 90; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
225 | GROUNDING PLOT PLAN |  | 0.07 |  |  |  | 14: 70; 15: 90; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
226 | GROUNDING PLOT PLAN |  | 0.07 |  |  |  | 14: 70; 15: 90; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
227 | GROUNDING PLOT PLAN |  | 0.07 |  |  |  | 14: 70; 15: 90; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
228 | GROUNDING PLOT PLAN |  | 0.07 |  |  |  | 14: 70; 15: 90; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
229 | ELECTRICAL GROUNDING DETAILS |  | 0.07 |  |  |  | 14: 70; 15: 90; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
230 | ELECTRICAL GROUNDING DETAILS |  | 0.07 |  |  |  | 14: 70; 15: 90; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
231 | ELECTRICAL GROUNDING DETAILS |  | 0.07 |  |  |  | 14: 70; 15: 90; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
232 | ELECTRICAL GROUNDING DETAILS |  | 0.07 |  |  |  | 14: 70; 15: 90; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
233 | ELECTRICAL GROUNDING DETAILS |  | 0.07 |  |  |  | 14: 70; 15: 90; 16: 90; 17: 90; 18: 90; 19: 90; 20: 90
234 | P 204 A/B LOGIC FLOW DIAGRAM |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
235 | P 205 A/B LOGIC FLOW DIAGRAM |  | 0.07 |  |  |  | 14: 70; 15: 70; 16: 80; 17: 80; 18: 80; 19: 80; 20: 80
82 | 90% Design Engineering 10, 20, 30, 40, 50, 60, 70 series drawings | 30 |  |  | 9
83 | Index 90 % | 0 | 30 | 2 | 9 | 10 | 1: 0; 2: 0; 3: 0; 4: 0; 5: 0; 6: 0; 18: 70; 19: 70; 20: 70
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| PIPING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ONE LINE DIAGRAM-EMERGENCY GENERATOR ENCLOSURE |  | 0.07 |  |  |  | 19: 80; 20: 80
| PANEL SCHEDULE-208/3ø, LP-MCC WATER BLDG-LP, MCC COMP |  | 0.07 |  |  |  | 19: 80; 20: 80
| PROT. RELAY & LOCKOUT RELAY TRIP SCHEDULE-GTG-100, 200 & 300 |  | 0.07 |  |  |  | 19: 80; 20: 80
| 86 LOCKOUT/TRIPPING RELAY SCHEDULE-GTG-100, 200 & 300 |  | 0.07 |  |  |  | 19: 80; 20: 80
| EQUIPMENT DRAWING-SYNCH CONTROL PANEL SP-100/200/300 |  | 0.07 |  |  |  | 19: 80; 20: 80
| EQUIPMENT DRAWING-SYNCH CONTROL PANEL SP-100/200/300 |  | 0.07 |  |  |  | 19: 80; 20: 80
| EQUIPMENT DRAWING-OUTSIDE AREA LGHTG PANEL ALP-2A |  | 0.07 |  |  |  | 19: 80; 20: 80
| EQUIPMENT DRAWINGS-ESD PANEL 1 THRU 5 |  | 0.07 |  |  |  | 19: 80; 20: 80
| CONTROL SCHEMATIC-400V LIGHTING EQUIPMENT LP-1 |  | 0.07 |  |  |  | 19: 80; 20: 80
| CONTROL SCHEMATIC-ESD & RAW WATER SOV |  | 0.07 |  |  |  | 19: 80; 20: 80
| WIRING DIAGRAM-FIBER OPTIC PANEL 1, CONTROL ROOM |  | 0.07 |  |  |  | 19: 80; 20: 80
| WIRING DIAGRAM-FIBER OPTIC PANEL 2, 3, 4, 7 & 8 |  | 0.07 |  |  |  | 19: 80; 20: 80
| CONTROL SCHEMATIC-DCS CABINET 1 |  | 0.07 |  |  |  | 19: 90; 20: 90
| CONTROL SCHEMATIC-DCS CABINET 2 |  | 0.07 |  |  |  | 19: 90; 20: 90
| CONTROL SCHEMATIC-DCS CABINET 3 |  | 0.07 |  |  |  | 19: 90; 20: 90
| HIGH SIDE SYNCHRONIZATION-CONTROL SCHEMATICS |  | 0.07 |  |  |  | 19: 80; 20: 80
| TYPICAL MANHOLE DETAILS |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| ELECTRICAL PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| GROUNDING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| GROUNDING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| GROUNDING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| GROUNDING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| GROUNDING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| GROUNDING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| GROUNDING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| GROUNDING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| GROUNDING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| GROUNDING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| GROUNDING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| GROUNDING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| GROUNDING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| GROUNDING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| GROUNDING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| GROUNDING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| GROUNDING PLOT PLAN |  | 0.07 |  |  |  | 19: 80; 20: 80
| T-1000 & T-1001 LOGIC FLOW DIAGRAM |  | 0.07 |  |  |  | 19: 70; 20: 70
| T-1002 & T-1003 LOGIC FLOW DIAGRAM |  | 0.07 |  |  |  | 19: 70; 20: 70
| T-1005 & T-1006 LOGIC FLOW DIAGRAM |  | 0.07 |  |  |  | 19: 70; 20: 70
| ELECTRICAL STUB UP DETAILS-GSU FOUNDATIONS |  | 0.07 |  |  |  | 19: 100; 20: 100
| ELECTRICAL STUB UP DETAILS-UTILITY/ELECTRICAL BUILDING |  | 0.07 |  |  |  | 19: 100; 20: 100
| ELECTRICAL STUB UP DETAILS-WATER TREATMENT BUILDING |  | 0.07 |  |  |  | 19: 100; 20: 100
| ELECTRICAL STUB UP DETAILS-MCC/GAS COMPRESSOR BUILDING |  | 0.07 |  |  |  | 19: 100; 20: 100
| ELECTRICAL STUB UP DETAILS-CONTROL ROOM |  | 0.07 |  |  |  | 19: 100; 20: 100
| ELECTRICAL STUB UP DETAILS-CENTRIFUGE PACKAGE |  | 0.07 |  |  |  | 19: 100; 20: 100
| ELECTRICAL STUB UP DETAILS-FOAM BUILDING |  | 0.07 |  |  |  | 19: 100; 20: 100
84 | Issue for Construction Drawings | 10 | 10 | 2 | 9 | 10 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20
|  |  | 100 |  |  |  | 5.088 | 5.088 | 5.088 | 5.088 | 5.088 | 5.088 | 12.808 | 14.352 | 14.352 | 15.609 | 16.406 | 16.526 | 16.526 | 28.027 | 43.036 | 49.417 | 50.05 | 71.05 | 79.002 | 79.058 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## ANADES
Planta la Raisa |  | SEMANA: |  | 9
CONSTRUCCION
Codigo |  | Peso | PROGRESO |  |  | APORTE |  |  | ATRASO |  | ADELANTO
| Actividades/Partidas | (%) | PROG. | REAL | DIF. | PROG. | REAL | DIF. | NETO | APORTE | NETO | APORTE
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
2 | COVER SHEET | #REF! | 100 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
3 | MECHANICAL LEGENDS, SYMBOLS AND ABBREVIATIONS | #REF! | 100 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | 100 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! | 100 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
4 | ELECTRICAL LEGENDS, SYMBOLS AND ABBREVIATIONS | #REF! |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
5 | ELECTRICAL NOTES | #REF! | 100 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! |  | #REF!
6 | ELECTRICAL ABBREVIATIONS | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
7 | INSTRUMENTATION LEGENEDS, SYMBOLS AND ABBREVIATIONS | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
8 | STRUCTURAL GENERAL NOTES | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
9 | STANDARD CONCRETE DETAILS | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
10 | GENERAL ARRANGEMENT PLOT PLAN-FT8-3 SWIFT PAC GTG UNITS | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
11 | ROUGH GRADING PLAN | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
12 | FOUNDATION LOCATION PLAN | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
13 | FOUNDATION PLAN-FT8 GAS TURBINE GENERATOR GTG-100, GTG-200 | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
14 | FOUNDATION SECTIONS-FT8 GAS TURBINE GENERATOR GTG-100, GTG-200 | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
15 | MAJOR EQUIP. ANCHOR BOLT PLAN-FT8 GAS TURBINE GENERATOR GTG-100, GTG-200 | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
16 | FLOOR PITCH AND DRAIN PLAN-FT8 GAS TURBINE GENERATOR GTG-100, GTG-200 | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
17 | JACKING PLATE/BAR LOCATION PLAN-FT8 GAS TURBINE GENERATOR GTG-100, GTG-200 | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
18 | CONCRETE FINISH PLAN-FT8 GAS TURBINE GENERATOR GTG-100, GTG-200 | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
19 | FOUNDATION REINFORCING BAR PLAN-FT8 GAS TURBINE GENERATOR GTG-100, GTG-200 | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
20 | REINFORCING BAR SCHEDULE AND DETAILS-FT8 GAS TURBINE GENERATOR GTG-100, GTG-200 | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
21 | PROCESS FLOW DIAGRAM-THREE (3) P & W FT8-3 SWIFT PAC UNITS | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
22 | PROCESS FLOW DIAGRAM-THREE (3) P & W FT8-3 SWIFT PAC UNITS | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
23 | PROCESS FLOW DIAGRAM-THREE (3) P & W FT8-3 SWIFT PAC UNITS | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
#REF! | #REF! | #REF! |  |  | 0 | #REF! | #REF! | #REF! | #REF! |  | #REF!
| TOTAL ACUMULADO | #REF! | #REF! | #REF! | #REF! | - | - | - | #REF! | 0% | #REF! | 0%
Note on E1: COLOCAR AQUI EL NUMERO DE LA SEMANA CORRESPONDIENTE

## CURVES
Semana No. 9
Avance Físico Programado. | Ingenieria
Avance Físico Real
Avance Financiero Programado
Avance Financiero Real
Al 12/02/09
Desviacion de :
4.81