## Recap
ProEnergy EPC
Job Description: |  |  | "Two Pratt Whitney FT4 Twin Paks SC"
RECAP OF COST ESTIMATE
(1,000'S)
Project Name: |  |  | Barinas I Power Plant |  |  |  |  | Date: | 2011-10-26
Customer: |  |  | PDVSA |  |  |  |  | Quote No: | T 1003
Location: |  |  | Barinas, Venn |  |  |  |  | Est By:
Bid Due Date: | [7 empty] | RHL-civil by Derwick-as sold
I. Balance of Plant | [9 empty] | US $ | BsF
| 100 Civil Structural | [9 empty] | 8.5
|  | 101 | Site Preparation |  |  |  | 0 | calc |  | 0 | 0
|  | 102 | Excavation - Fill |  |  | Mhrs | 0 | calc |  | 0 | 0
|  | 103 | Concrete Foundations |  |  | 0 | 0 | calc |  | 0 | 0
|  | 104 | Concrete Pilings |  |  |  | 0 | calc
|  | 105 | Paving Asphalt - Concrete |  |  |  | 0 | calc |  | 0 | 0
|  | 106 | Gravel - Sand |  |  |  | 0 | calc |  | 0 | 0
|  | 107 | Structual Steel |  |  |  | 95 | calc |  | 23.75 | 605.625
|  | 108 | Fencing |  |  |  | 0 | calc |  | 0 | 0
|  | 109 | Architectual Treatment |  |  |  | 0 | calc
|  | 110 | Evaporation Pond |  |  |  | 0 | calc
[7 empty] | 95 |  | 95
| 200 Buildings | [5 empty] | 331.25 | calc | 331.25 | 331.25
| 300 Mechanical |  |  |  |  | Mhrs
|  | 310 | Major Mechanical Equipment |  |  |  | 4644 | calc |  | 4644
|  | 320 | Pipe, Valves & Fitting labor |  |  | 35100 | 2036.4704 | calc |  | 509.1176 | 12982.4989
|  | 330 | Mechanical Subcontractor |  |  | 28062 | 1628.132 | calc |  | 407.033 | 10379.3414
|  | 340 | Pipe, Valves & Fitting Material |  |  |  | 900 | calc |  | 900
[7 empty] | 9208.6024 |  | 9208.6024
400 Electrical
|  | 410 | Major Electrical Equipment |  |  |  | 966.2 | calc |  | 966.2
|  | 420 | Substation Equipment |  |  |  | 1201.6 | calc |  | 1201.6
|  | 430 | Plant Electrical Subcontractor |  |  | 19148.4 | 1110.9729 | calc |  | 277.7432 | 7082.4525
|  | 440 | Substation Subcontractor |  |  | 6544.8 | 379.7234 | calc |  | 94.9309 | 2420.7367
|  | 450 | Conduit, Cable & Wire Material |  |  |  | 900 | calc |  | 900 |  |  | HV revised budget 24oct2011
|  | 460 | Conduit, Cable & Wire Labor |  |  | 28080 | 1629.1763 | calc |  | 407.2941 | 10385.9991 |  | USD | BsF
[12 empty] | sub equip | 1201600
[7 empty] | 6187.6727 |  | 6187.6727 |  |  | sub subcon | 94930.8514 | 2420736.7112
[12 empty] | TSD add/25% margin | 0
| 500 Instrumentation | [10 empty] | before margin= | 1296530.8514 | 2420736.7112
|  | 510 | CEMS |  |  |  | 0 | calc
|  | 520 | Plant Instrumentation |  |  |  | 125 | calc
|  | 530 | Instrumentation Subcontractor |  |  | 1440 | 83.5475 | calc
[7 empty] | 208.5475 |  | 208.5475 | 208.5475
600 DCS System / Communications
|  | 610 | Hardware / Software |  |  |  | 685 | calc
|  | 620 | Telephone System |  |  |  | 15 | calc
|  | 630 | Public Address System |  |  |  | 15 | calc
|  | 640 | TV / Security |  |  |  | 0 | calc
[7 empty] | 715 |  | 715 | 715
700 Plant Erection
|  | 700 | Plant Erection |  |  | 21600 | 1253.2126 | calc
|  | 750 | Plant Dismantling |  |  |  | 0 | plgd/1000
|  | 755 | Plant Dismantling Labor |  |  |  | 0 | plgd/1000
|  |  |  | Total El/Mech Mhrs |  | 139975.2 | 1253.2126 |  | 1253.2126 | 313.3031 | 7989.2301
| 800 Equipment Rental | [5 empty] | 988.25 | calc | 988.25 | 247.0625 | 6300.0938
| 900 Painting | [5 empty] | 285 | calc | 285 | 71.25 | 1816.875
1000 Transportation
|  | 1001 | US Inland Transportation |  |  |  | 608.12 | calc |  | 608.12
|  | 1002 | Ocean/Air Freight |  |  |  | 600 | plgd /1000 |  | 600
|  | 1003 | Destination Inland Freight |  |  |  | 400 | plgd /1000 |  |  | 3400
|  | 1004 | Customs / Duties (plant equip & mat'l) |  |  |  | 0 | plgd /1000
|  | 1005 | Unload & Receive Mat'l at Site (Relocate FT4's) |  |  |  | 200 | plgd /1000 |  |  | 1700
|  | 1006 | Receive, Inspect, Inventory |  |  |  | 0 | plgd /1000
|  | 1007 | Storage of FT4 Equipment & GSU's) |  |  |  | 150 | plgd /1000 |  |  | 1275
|  | 1008 | Local Registrations Fees, License, Etc. |  |  |  | 0 | plgd /1000
|  | 1009 | Transport of Damaged Goods for Repair |  |  |  | 0 | plgd /1000
[7 empty] | 1958.12 |  | 1958.12
| 1100 Site Costs | [5 empty] | 623.8 | calc | 623.8 |  | 5302.3
1200 Engineering
|  | 1201 | EPC Eng Labor |  |  |  | 1205 | calc
|  | 1202 | Local Eng |  |  |  | 360 | calc
[7 empty] | 1565 |  | 1565 | 1565
1300 Project Management
|  | 1310 | Project & Construction |  |  |  | 2054 | calc
|  | 1320 | Inspectors |  |  |  | 368 | calc
[7 empty] | 2422 |  | 2422 | 2422
| 1400 Travel & Perdiem | [5 empty] | 892.75 | calc
|  | 1410 | Project Meal Expense |  |  |  | 0 | calc
[7 empty] | 892.75 |  | 892.75 | 892.75
| 1500 Technical Reps |  |  |  |  | $/day
|  | 1501 | GTG Tech Rep |  | 150 | 2000 | 300 | plgd /1000
|  | 1502 | Fire Water |  | 0 | 2000 | 0 | plgd /1000
|  | 1503 | Gas Compressor |  | 0 | 2000 | 0 | plgd /1000
|  | 1504 | Chiller |  | 0 | 2000 | 0 | plgd /1000
|  | 1505 | Water Treatment |  | 15 | 1800 | 27 | plgd /1000
|  | 1506 | Commission / S/U / Trng |  | 80 | 1800 | 144 | plgd /1000
|  | 1507 | Controls Rep |  | 20 | 2000 | 40 | plgd /1000
|  | 1508 | DFO Treatment |  | 15 | 2000 | 30 | plgd /1000
|  | 1509 | SCR |  | 0 | 2000 | 0 | plgd /1000
[7 empty] | 541 |  | 541 | 541
1600 Project Tests
|  | 1601 | Soil Boring / Compaction |  |  |  | 20 | plgd /1000
|  | 1602 | Concrete |  |  |  | 40 | plgd /1000
|  | 1603 | X Ray |  |  |  | 40 | plgd /1000
|  | 1604 | Plant Performance and Reliability |  |  |  | 100 | plgd /1000
|  | 1605 | Emission Tests |  |  |  | 0 | plgd /1000
|  | 1606 | Protective Relays |  |  |  | 20 | plgd /1000
|  | 1607 | Acoustics / Noise Test |  |  |  | 0 | plgd /1000
[7 empty] | 220 |  | 220 | 220
| 1700 Legal | [5 empty] | 0 | plgd /1000 | 0
1800 Insurance / Securities
|  | 1810 | Bonds |  |  |  | 0 | plgd /1000
|  | 1820 | Buildiers All Risk |  |  |  | 300 | plgd /1000
|  | 1830 | Marine / Cargo |  |  |  | 0 | plgd /1000
|  | 1840 | Professional |  |  |  | 0 | plgd /1000
[7 empty] | 300 |  | 300 | 300
| 1900 Taxes | [5 empty] | 0 | calc | 0
| 2000 Commissions | [5 empty] | 0 | plgd /1000 | 0
2100 Project Contingency / Risk
|  | 2110 | Project Contingency |  |  |  | 1000 | plgd / 1000
|  | 2120 | GT Performance |  |  |  | 0 | plgd / 1000
|  | 2130 | Schedule LD |  |  |  | 0 | plgd / 1000
|  | 2140 | Material Escalation |  | 5% | 9451.8 | 472.59 | calc
|  | 2150 | Labor Contingency |  | 5% | 8121.2351 | 406.0618 | calc
[7 empty] | 1878.6518 |  | 1878.6518 | 1878.6518
[5 empty] | BOP Cost |  |  |  | 29673.8569 | 21245.6037 | 71640.1523
[5 empty] | % Markup |  |  | 25% | 7418.4642 | 7418.4642 | 0
[5 empty] | BOP US$ Cost + Markup |  |  |  | 37092.3211
[10 empty] | US$ | BsF
[5 empty] | BOP Sales Price |  |  |  | 37092.3211 | 28664.0679 | 71640.1523
[5 empty] | Local Municipal & Social |  |  | 7.5% |  |  | 5373.0114
[5 empty] | IVA |  |  | 16% |  |  | 11462.4244
[5 empty] | Total BOP Sales Price Incl. Taxes |  |  |  |  | 28664.0679 | 88475.5881
[5 empty] | AS SOLD PRICE |  |  |  |  | 30537.944 | 103911.559
[5 empty] | SWAP BsF46MM @ 8.1 ER |  |  |  |  | -5679.0123 | 46000
[5 empty] | ADJUSTED AS SOLD PRICE |  |  |  |  | 24858.9317 | 149911.559
[5 empty] | MULTIPLY BY 1000 = |  |  |  |  | 24858931.6543 | 149911559
[5 empty] | AS SOLD MARGIN |  |  |  |  | 9292.3403 | 0
[5 empty] | STANDARD 25% MARGIN |  |  |  |  | 7418.4642 | 0
[5 empty] | EXCESS MARGIN |  |  |  |  | 1873.8761 | 0
[5 empty] | MARGIN AFTER ADJUSTED AS SOLD PRICE |  |  |  |  | 3613.328 | 46000
[5 empty] | BUDGET AFTER ADJUSTED AS SOLD PRICE |  |  |  |  | 21245603.6659 | 103911559

## 101 Site Prep
|  |  | SITE PREP | [6 empty] | 101
(1,000's)
Project Name: |  | Barinas I Power Plant | [5 empty] | Date: |  | 2011-10-26
Customer: |  | PDVSA | [5 empty] | Quote No: |  | T 1003
Location: |  | Barinas, Venn | [5 empty] | Est By: |  | RHL-civil by Derwick-as sold
Bid Due Date:
Item |  | Description |  | "L" | "W" | "D" | Cubic | Cubic | Price | Total
No. |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price
1 | Clearing/Grubbing - main plant |  |  | 0 | 450 | 1 | 0 | 0 | 24 | 0
2 | Clearing/Grubbing - fuel unload |  |  | 0 | 680 | 1 | 0 | 0 | 24 | 0
3 | Remove Concrete Foundations |  |  | 0 | 100 | 3 | 0 | 0 | 430 | 0
4
5 | Remove Contaminated Soil |  |  | 0 | 150 | 2 | 0 | 0 | 60 | 0
6 | [6 empty] | 0 | 0
7 | Dump Trucks to Drop Site |  |  | 0 |  |  | 0 | 0 | 85 | 0
8 | [6 empty] | 0 | 0
9 | Cost to Dump |  |  | 0 |  |  | 0 | 0 | 40 | 0
10 | [6 empty] | 0 | 0
11 | Trucks to bring in new dirt |  |  | 0 |  |  | 0 | 0 | 85 | 0
12 | [6 empty] | 0 | 0
13 | Cu Yards new dirt in place |  |  | 0 |  |  | 0 | 0 | 20 | 0
14
15 | Tunnels
16
17 | Wells
18
19 | Containment System Rework |  |  | 0 | 6 | 4 | 0 | 0 | 35 | 0
20 | [6 empty] | 0
21 | Black Top Liner |  |  | 0 | 400 | 0.1 | 0 | 0 | 25 | 0
22 | [6 empty] | 0
23 | Masonry | [5 empty] | 0
24
25
26
27
28
29
30
31
32
33
34
0

## 102 Excavation
|  |  |  | EXCAVATION AND FILL | [6 empty] | 102
(1,000's)
Project Name: |  | Barinas I Power Plant | [6 empty] | Date: |  | 2011-10-26
Customer: |  | PDVSA | [6 empty] | Quote No: |  | T 1003
Location: |  | Barinas, Venn | [6 empty] | Est By: |  | RHL-civil by Derwick-as sold
Bid Due Date:
Item |  | Description |  |  | "L" | "W" | "D" | Cubic | Cubic | Price | Total
No. |  |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price
1 | Bldg Area
2 | Fuel Gas Compressor Shed |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
3 | Control/Office/Maint |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
4 | Water Treatment Area |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
5 | Electric Bldg |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
6 | Pwr Blk Utility Bldg |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
7 | Substation Bldg |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
8 | Steam Turbine Hall |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
9 | Liquid Fuel Unloading Shed |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
10
11 | Main Plant Area |  |  |  | 0 | 450 | 1 | 0 | 0 | 18 | 0
12 | Fuel Unloading Area |  |  |  | 0 | 680 | 1 | 0 | 0 | 18 | 0
13
14 | Fill |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
15 | Substation Area |  |  |  | 0 | 0 | 0 | 0 | 0 | 9 | 0
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45 |  |  | Total Cost of Excavation and Fill | [7 empty] | 0

## 103 Foundations
|  |  |  | CONCRETE FOUNDATIONS | [6 empty] | 103
(1,000's)
Project Name: |  | Barinas I Power Plant | [7 empty] | Date: | 2011-09-22
Customer: |  | PDVSA | [7 empty] | Quote No: | T 1003
Location: |  | Barinas, Venn | [7 empty] | Est By: | RHL-civil by Derwick-as sold
Bid Due Date:
Item |  | Description |  | Qty | "L" | "W" | "D" | Cubic | Cubic | Price | Total | 5
No. |  |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price | mhr/cy
1 | POWER ISLAND |  |  | Price: 800
2 | GT Generators FT 4 Twin Pak |  |  | 0 | 110 | 40 | 4 | 0 | 0 | 800 | 0 | 0
3 | Exhaust Stack |  |  | 0 | 25 | 25 | 4 | 0 | 0 | 800 | 0 | 0
4 | HRSG |  |  | 0 | 75 | 16 | 4 | 0 | 0 | 800 | 0 | 0
5 | SCR |  |  | 0 | 52 | 16 | 4 | 0 | 0 | 800 | 0 | 0
6 | STG |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0
7 | STG Cooling Tower |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0
8 | STG Inlet Chillers |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0
9 | STG Condenser Fndn |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0
10 | Aux Skid(s) for GTG |  |  | 0 | 30 | 40 | 2 | 0 | 0 | 800 | 0 | 0
11
12
13 | BALANCE OF PLANT
14 | Chiller Cooling Tower |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0
15 | Fuel Gas Regulator Skid |  |  | 0 | 18 | 8 | 1 | 0 | 0 | 800 | 0 | 0
16 | Fuel Gas GTG Meter Skid |  |  | 0 | 25 | 6 | 1 | 0 | 0 | 800 | 0 | 0
17 | Fin Fan L O Coolers |  |  | 0 | 15 | 15 | 2 | 0 | 0 | 800 | 0 | 0
18 | Gas Compressors |  |  | 0 | 45 | 15 | 3 | 0 | 0 | 800 | 0 | 0
19 | Fuel Gas Plant Metering Skid |  |  | 0 | 15 | 8 | 1 | 0 | 0 | 800 | 0 | 0
20 | Comp Fin Fans |  |  | 0 | 15 | 15 | 1 | 0 | 0 | 800 | 0 | 0
21 | Waste Oil/Water Storage Tank |  |  | 0 | 15 | 12 | 2 | 0 | 0 | 800 | 0 | 0
22 | Oily Water Separator |  |  | 0 | 30 | 20 | 2 | 0 | 0 | 800 | 0 | 0
23 | Lubricant Storage Area |  |  | 0 | 45 | 30 | 1 | 0 | 0 | 800 | 0 | 0
24 | Instrument Air Comp Skid |  |  | 0 | 10 | 8 | 1 | 0 | 0 | 800 | 0 | 0
25 | Pipe Rack Stanchons |  |  | 0 | 2.5 | 2.5 | 6 | 0 | 0 | 800 | 0 | 0
26 | 15KV Cable Tray Stanchons |  |  | 0 | 2.5 | 2.5 | 6 | 0 | 0 | 800 | 0 | 0
27 | Fire Water Pump Skid |  |  | 0 | 15 | 30 | 2 | 0 | 0 | 800 | 0 | 0
28 | Area Light Poles |  |  | 0 | 2.5 | 3 | 5 | 0 | 0 | 800 | 0 | 0
29 | Aux Trans fndns |  |  | 0 | 10 | 15 | 1.5 | 0 | 0 | 800 | 0 | 0
30 | Cable Trenches see est |  |  | 0 | 350 | 4 | 4 | 0 | 0 | 800 | 0 | 0
31 | Water Treatment Plant |  |  | 0 | 40 | 40 | 2 | 0 | 0 | 800 | 0 | 0
32 | DFO Unloading Rack |  |  | 0 | 60 | 50 | 2 | 0 | 0 | 800 | 0 | 0
33 | DFO Forward Pump skid |  |  | 0 | 8 | 6 | 2 | 0 | 0 | 800 | 0 | 0
34 | DFO Transfer Pump skid |  |  | 0 | 8 | 6 | 2 | 0 | 0 | 800 | 0 | 0
35 | Demin Water Pump skid |  |  | 0 | 8 | 6 | 2 | 0 | 0 | 800 | 0 | 0
36 | Demin Stg Tanks ____ Gal |  |  | 0 | 15 | 15 | 2 | 0 | 0 | 800 | 0 | 0
37 | Demin Forwarding Pumps |  |  | 0 | 6 | 4 | 1 | 0 | 0 | 800 | 0 | 0
38 | DFO Metering Skid |  |  | 0 | 15 | 6 | 1 | 0 | 0 | 800 | 0 | 0
39 | Raw Water Tank Base |  |  | 0 | 25 | 25 | 2 | 0 | 0 | 800 | 0 | 0
40 | Fire Water Tank base |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0
41 | Emer Generator Base |  |  | 0 | 25 | 15 | 2 | 0 | 0 | 800 | 0 | 0
42 | DFO Raw Fuel Tank |  |  | 0 | 40 | 40 | 2 | 0 | 0 | 800 | 0 | 0
43 | DFO Clean Fuel Tank |  |  | 0 | 30 | 30 | 2 | 0 | 0 | 800 | 0 | 0
44 | DFO Centrifuges Skid |  |  | 0 | 18 | 8 | 2 | 0 | 0 | 800 | 0 | 0
45 | DFO Pump Skid |  |  | 0 | 7 | 5 | 1 | 0 | 0 | 800 | 0 | 0
46 | Sludge Tank |  |  | 0 | 15 | 15 | 1 | 0 | 0 | 800 | 0 | 0
47 | Sludge Pump Skid |  |  | 0 | 7 | 5 | 1 | 0 | 0 | 800 | 0 | 0
48 | BUILDINGS
49 | Control Bldg/Office |  |  | 0 | 140 | 60 | 1 | 0 | 0 | 800 | 0 | 0
50 | Warehouse/Maintenance |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0
51 | Water Treatment Bldg |  |  | 0 | 30 | 40 | 2 | 0 | 0 | 800 | 0 | 0
52 | Gas Compressor Bldg |  |  | 0 | 120 | 45 | 1 | 0 | 0 | 800 | 0 | 0
53 | Electrical Bldg |  |  | 0 | 42 | 20 | 1 | 0 | 0 | 800 | 0 | 0
54 | Pwr Blk Utility Bldg's |  |  | 0 | 30 | 20 | 1 | 0 | 0 | 800 | 0 | 0
55 | Substation Bldg |  |  | 0 | 15 | 12 | 1 | 0 | 0 | 800 | 0 | 0
56 | Steam Turbine Hall |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0
57 | Liquid Fuel Unloading |  |  | 0 | 60 | 40 | 2 | 0 | 0 | 800 | 0 | 0
58 | DFO Treatment Shed |  |  | 0 | 35 | 20 | 2 | 0 | 0 | 800 | 0 | 0
59 | Control Room |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 800 | 0 | 0
60
61 | SUBSTATION
62 | GSU Transformer |  |  | 0 | 30 | 30 | 3 | 0 | 0 | 800 | 0 | 0
63 | (___)KV SF6 Circuit Breaker |  |  | 0 | 15 | 15 | 2 | 0 | 0 | 800 | 0 | 0
64 | (___)KV Disc Switch w/ Stand |  |  | 0 | 10 | 15 | 2 | 0 | 0 | 800 | 0 | 0
65 | Dead End Tower |  |  | 0 | 15 | 10 | 3 | 0 | 0 | 800 | 0 | 0
66 | Transmission Line Poles |  |  | 0 | 5 | 5 | 20 | 0 | 0 | 800 | 0 | 0
67 | Insulator Support Base |  |  | 0 | 3 | 3 | 5 | 0 | 0 | 800 | 0 | 0
68 | PT Support Base |  |  | 0 | 3 | 3 | 5 | 0 | 0 | 800 | 0 | 0
69 | GSU Blast Wall |  |  | 0 | 45 | 25 | 2 | 0 | 0 | 800 | 0 | 0
70
71
72 |  |  | Total Cost of Foundations | Cubic: 0; Total: 0 | 0
Note on K12: Insert Rate Here:

## 104 Pilings
PILINGS
|  |  |  | (1,000's) | [7 empty] | 104
Project Name: |  | Barinas I Power Plant | [7 empty] | Date: |  | 2011-10-26
Customer: |  | PDVSA | [7 empty] | Quote No: |  | T 1003
Location: |  | Barinas, Venn | [7 empty] | Est By: |  | RHL-civil by Derwick-as sold
Bid Due Date:
Item |  | Description | [7 empty] | Cu | Price | Total
No. |  |  |  |  | Units | Qty | "L" | "D" | "W" | Yd | CuYd | Price
1 | Concrete Pilings
2 | Pilings GTG x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 450 | 0
3 | Pilings SCR x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Pilings GSU x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | Pilings Gas Comp x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Pilings HRSG x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Pilings STG x _____ |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45 |  |  | Total Cost of Retaining Walls |  | Total Price: 0

## 105 Paving
PAVING ASPHALT - CONCRETE
|  |  |  | (1,000's) | [5 empty] | 105
Project Name: |  | Barinas I Power Plant | [6 empty] | Date: | 2011-10-26
Customer: |  | PDVSA | [6 empty] | Quote No: | T 1003
Location: |  | Barinas, Venn | [6 empty] | Est By: | RHL-civil by Derwick-as sold
Bid Due Date:
Item |  | Description |  | "L" | "W" | "D" | Cubic | Cubic | Price | Total
No. |  |  |  | Ft | Ft | Ft | Ft | Yds | Yd | Price
1 | Concrete |  |  | 0 | 0 | 0 | 0 | 0 | 600 | 0
2 | Gen Removal Areas |  |  | 0 | 20 | 1 | 0 | 0 | 600 | 0
3 | Turbine Removal Areas |  |  | 0 | 20 | 1 | 0 | 0 | 600 | 0
4 | Entry Ways |  |  | 0 | 8 | 0.5 | 0 | 0 | 600 | 0
5 | Walk ways |  |  | 0 | 0 | 0 | 0 | 0 | 600 | 0
6 |  |  |  | 0 | 0 | 0 | 0 | 0 | 600 | 0
7
8
9 |  |  |  | "L" | "W" | "D" | Cubic | Cubic | Price
10 | Asphalt |  |  | Ft | Ft | Ft | Ft | Yds | Yd
11 | Roadways |  |  | 0 | 20 | 0.8 | 0 | 0 | 600 | 0
12 | Parking Lot |  |  | 0 | 0 | 0 | 0 | 0 | 600 | 0
13 | [6 empty] | 0 | 0 |  | 0
14 | LFO Trucks Unloading Area |  |  | 0 | 20 | 0.8 | 0 | 0 | 600 | 0
15 | [6 empty] | 0 | 0 |  | 0
16 | [6 empty] | 0 | 0 |  | 0
17 | [6 empty] | 0 | 0 |  | 0
18 | [6 empty] | 0 | 0 |  | 0
19 | [6 empty] | 0 | 0 |  | 0
20 | [6 empty] | 0 | 0 |  | 0
21 | [6 empty] | 0 | 0 |  | 0
22 | [6 empty] | 0 | 0 |  | 0
23 | [6 empty] | 0 | 0 |  | 0
24 | [6 empty] | 0 | 0 |  | 0
25 | [6 empty] | 0 | 0 |  | 0
26 | [6 empty] | 0 | 0 |  | 0
27 | [6 empty] | 0 | 0 |  | 0
28 | [6 empty] | 0 | 0 |  | 0
29 | [6 empty] | 0 | 0 |  | 0
30 | [6 empty] | 0 | 0 |  | 0
31 | [6 empty] | 0 | 0 |  | 0
32 | [6 empty] | 0 | 0 |  | 0
33 | [6 empty] | 0 | 0 |  | 0
34 | [6 empty] | 0 | 0 |  | 0
35 | [6 empty] | 0 | 0 |  | 0
36 | [6 empty] | 0 | 0 |  | 0
37 | [6 empty] | 0 | 0 |  | 0
38 | [6 empty] | 0 | 0 |  | 0
39 | [6 empty] | 0 | 0 |  | 0
40 | [9 empty] | 0
Note on J12: Insert Rate Here:

## 106 Gravel - Sand
GRAVEL
[5 empty] | (1,000's) | [6 empty] | 106
Project Name: |  | Barinas I Power Plant | [7 empty] | Date: |  | 2011-10-26
Customer: |  | PDVSA | [7 empty] | Quote No: |  | T 1003
Location: |  | Barinas, Venn | [7 empty] | Est By: |  | RHL-civil by Derwick-as sold
Bid Due Date:
Item |  | Description |  | Qty | "L" | "W" | "D" | Cubic | Cubic | Tons | Price | Total
No. |  |  |  |  | Ft | Ft | Ft | Ft | Yds |  | /Ton | Price
1
2 | Main Plant Area (less substa) |  |  | 0 | 400 | 450 | 0.5 | 0 | 0 | 0 | 25 | 0
3
4 | Cooling Tower Area |  |  | 0 | 110 | 160 | 0.5 | 0 | 0 | 0 | 25 | 0
5
6 | Substation |  |  | 0 | 150 | 150 | 1 | 0 | 0 | 0 | 25 | 0
7
8 | Road ways |  |  | 0 | 1200 | 20 | 0.5 | 0 | 0 | 0 | 25 | 0
9
10 | New Laydown Area |  |  | 0 | 300 | 300 | 0.5 | 0 | 0 | 0 | 25 | 0
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Gravel | Total: 0

## 107 Structural
STRUCTUAL STEEL
[5 empty] | (1,000's) |  |  |  | 107
Project Name: |  | Barinas I Power Plant | [5 empty] | Date: | 2011-10-26
Customer: |  | PDVSA | [5 empty] | Quote No: | T 1003
Location: |  | Barinas, Venn | [5 empty] | Est By: | RHL-civil by Derwick-as sold
Bid Due Date:
Item |  | Description |  |  |  | # of | Qty | Price | Total
No. | [5 empty] | Lbs / Tons |  |  | Price
1
2
3 | Misc Pipe Rack supports etc. | [5 empty] | 10 | 3000 | 30000
4 | [8 empty] | 0
5 | 15 KV Cable Tray Stanchons | [5 empty] | 10 | 2500 | 25000
6 | [8 empty] | 0
7 | GTG walkways and stairs | [5 empty] | 2 | 5000 | 10000
8 | [8 empty] | 0
9 | Structual Steel for equip supports | [5 empty] | 0 | 0 | 0
10
11 | Overhead Crane (Bldg) (______) Ton | [5 empty] | 0 | 0 | 0
12
13 | Steel Cover for Storm Water Catch Basin | [5 empty] | 0 | 0 | 0
14
15 | Steel Grating Walkways over pipe ways/ Comp Bldg | [5 empty] | 0 | 0 | 0
16
17 | Misc Walkways, Platforms, & Stairs | [5 empty] | 1 | 30000 | 30000
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41 |  |  | Total Cost of Stuctual Steel | [5 empty] | 95

## 108 Fence
FENCING
[5 empty] | (1,000's) |  |  | 108
Project Name: |  | Barinas I Power Plant |  |  |  |  | Date: | 2011-10-26
Customer: |  | PDVSA |  |  |  |  | Quote No: | T 1003
Location: |  | Barinas, Venn |  |  |  |  | Est By: | RHL-civil by Derwick-as sold
Bid Due Date:
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [5 empty] | or Ftg | Price | Price
1 | Fencing
2 | Construction Lay Down Area |  |  |  |  | 0 | 15 | 0
3 | Site security |  |  |  |  | 0 | 0 | 0
4 | Permanent Site Fence, ___ High w/ ___ Strands Barbed Wire |  |  |  |  | 0 | 23 | 0
5 | Sub Station, ___ High w/ __ Strands Barbed Wire |  |  |  |  | 0 | 0 | 0
6 | Concret Base under fence 3ft H x1/2ft T x 1800 ft + 300 yds |  |  |  |  | 0 | 400 | 0
7
8 | Gates
9 | Manual Double Gate(s) |  |  |  |  | 0 | 3000 | 0
10 | Motor Operated Double Gate(s) |  |  |  |  | 0 | 7000 | 0
11 | Personnel Gate(s) |  |  |  |  | 0 | 600 | 0
12
13
14 | Intercom Station w/ Remote Button Operation on Gate |  |  |  |  | 0 | 6000 | 0
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Fencing |  |  |  |  | 0

## 200 Buildings
BUILDINGS
[5 empty] | (1,000's) |  |  |  | 200
Project Name: |  | Barinas I Power Plant | [5 empty] | Date: | 2011-10-26
Customer: |  | PDVSA | [5 empty] | Quote No: | T 1003
Location: |  | Barinas, Venn | [5 empty] | Est By: | RHL-civil by Derwick-as sold
Bid Due Date:
Item |  | Description |  |  | "L" | "W" | SqFt/ | Price | Total
No. |  |  |  |  | Ft | Ft | or Unit | Ft/Unit | Price
1 | Fuel Gas Compressor Shed |  |  |  | 0 | 0 | 0 | 0 | 0
2 | Control/Office |  |  |  | 0 | 0 | 0 | 0 | 0
3 | Water Treatment |  |  |  | 40 | 40 | 1600 | 50 | 80000
4 | Electric Bldg |  |  |  | 40 | 15 | 600 | 50 | 30000
5 | Warehouse/Maintenance |  |  |  | 0 | 0 | 0 | 0 | 0
6 | Substation Bldg |  |  |  | 0 | 0 | 0 | 0 | 0
7 | Steam Turbine Hall |  |  |  | 0 | 0 | 0 | 0 | 0
8 | Liquid Fuel Unloading Shed |  |  |  | 65 | 50 | 3250 | 50 | 162500
9 | DFO Treatment Shed |  |  |  | 35 | 25 | 875 | 50 | 43750
10 | Control Room |  |  |  | 0 | 0 | 0 | 0 | 0
11 | Entry Guard House |  |  |  | 20 | 15 | 300 | 50 | 15000
12 |  |  |  |  | 0 | 0 | 0 | 0 | 0
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39 |  |  | Total Cost of Other Buildings | [5 empty] | 331.25

## 310, 320, 330 & 340 Mechanical
MECHANICAL EQUIPMENT and Labor
(1,000's)
310 & 330
Project Name: |  | Barinas I Power Plant | [9 empty] | Date: |  | 2011-10-26
Customer: |  | PDVSA | [9 empty] | Quote No: |  | T 1003
Location: |  | Barinas, Venn | [9 empty] | Est By: |  | RHL-civil by Derwick-as sold
Bid Due Date:
Item |  | Description |  | Qty | Unit | Total | Unit | Frt | Hours | Qty | Qty | Qty | Rate | Total
No. |  |  |  |  | Price | Price | Frt Pr | Price | (day) | (men) | (days) | (mhrs) | (hour) | Labor
| GTG |  |  | Unit: 3%; Hours: 10
1 | GTG Type |  |  | 2 | 0 | 0 | 0 | 0 | 10 | 12 | 35 | 8400 | 58.0191 | 487360.44
2 | Lube oils and Chemicals |  |  | 2 | 50000 | 100000 | 3000 | 6000 | 10 | 0 | 0 | 0 | 58.0191 | 0
3 | Exhaust Stack |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
4 | Project Grouting |  |  | 2 | 55000 | 110000 | 3300 | 6600 | 10 | 0 | 0 | 0 | 58.0191 | 0
5 | GTG Tools |  |  | 1 | 50000 | 50000 | 1500 | 1500 | 10 | 0 | 0 | 0 | 58.0191 | 0
6 | Anchor Bolts |  |  | 0 | 55000 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
7
8 | HRSG
9 | HRSG Type |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
10 | Duct Burner / FD Fan |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
11 | HP BFW Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
12 | LB BFW Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
13 | Deaerator |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
14 | ByPass Diverter Valve |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
15
16 | SCR
17 | SCR w/ dilution fan, controls, etc. |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
18 | NH2 Tank w/ pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
19
20 | STG
21 | STG |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
22 | Condenser w/ ejectors |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
23 | Condenser Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
24 | Cooling Tower |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
25 | CW Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
26 | Chemical Inj Skid |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
27
28 | Inlet Air Conditioning System
29 | Inlet Chilling Package |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
30 | Inlet Fogging System |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
31 | Inlet Evap Cooling System |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
32 | Inlet Cooling System Cooling Tower |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
33 | Cooling Water Circulation Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
34 | Chilled Water Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
35 | Chemical Inj Skid |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
36
37 | Fuel Gas Systems
38 | Fuel Gas compressor w/ Fin Fans |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
39 | Fuel Gas Check Metering/Regulator Skid |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
40 | Fuel Gas Turbine Metering Skid |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
41 | Fuel Gas Filter Skid & Mnt (___) KW Htr(Htr in Elect) |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
42 | ESD Valve, ___" ___# |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
43
44 | Liquid Fuel Systems
45 | Unloading Pump Skid |  |  | 3 | 25000 | 75000 | 2250 | 6750 | 10 | 3 | 4 | 360 | 58.0191 | 20886.876
46 | Metering Skid |  |  | 1 | 155000 | 155000 | 4650 | 4650 | 10 | 3 | 4 | 120 | 58.0191 | 6962.292
47 | Forwarding Pump Skid |  |  | 1 | 35000 | 35000 | 1050 | 1050 | 10 | 3 | 4 | 120 | 58.0191 | 6962.292
48 | Transfer Pump Skid |  |  | 1 | 35000 | 35000 | 1050 | 1050 | 10 | 3 | 4 | 120 | 58.0191 | 6962.292
49 | Fuel Heating |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
50 | Filter Skid |  |  | 2 | 75000 | 150000 | 4500 | 9000 | 10 | 2 | 4 | 160 | 58.0191 | 9283.056
51 | Centrifuge |  |  | 3 | 220000 | 660000 | 40000 | 120000 | 10 | 6 | 8 | 1440 | 58.0191 | 83547.504
52 | Injection Pump Skid |  |  | 2 | 0 | 0 | 0 | 0 | 10 | 3 | 4 | 240 | 58.0191 | 13924.584
53 | Raw DFO Storage Tank Cleaning |  |  | 1 | 125000 | 125000 | 3750 | 3750 | 10 | 6 | 10 | 600 | 58.0191 | 34811.46
54 | Day Tank 600 M Gal CS Coated |  |  | 2 | 500000 | 1000000 | 20000 | 40000 | 10 | 6 | 5 | 600 | 58.0191 | 34811.46
55
56 | Water Supply System
57 | Raw/Fire Water Storage Tank 350 M gal |  |  | 1 | 400000 | 400000 | 5000 | 5000 | 10 | 4 | 4 | 160 | 58.0191 | 9283.056
58 | Raw Water Supply Pumps |  |  | 2 | 18000 | 36000 | 1080 | 2160 | 10 | 2 | 3 | 120 | 58.0191 | 6962.292
59 | Raw Water Forwarding Pumps |  |  | 2 | 18000 | 36000 | 1080 | 2160 | 10 | 2 | 3 | 120 | 58.0191 | 6962.292
60 | Water Well and Pump |  |  | 0 | 80000 | 0 | 0 | 0 | 0 | 4 | 3 | 0 | 58.0191 | 0
61 | Water Treatment System
62 | Multi Media Filter Package |  |  | 1 | 45000 | 45000 | 1350 | 1350 | 10 | 3 | 3 | 90 | 58.0191 | 5221.719
63 | Water Injection Skid |  |  | 0 |  | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
64 | Demin Treatment System 15 M Gal / Day |  |  | 1 | 200000 | 200000 | 6000 | 6000 | 10 | 5 | 6 | 300 | 58.0191 | 17405.73
65 | Demin Storage SS Tank gal |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
66 | Demin water fiberglass tank |  |  | 2 | 25000 | 50000 | 1500 | 3000 | 10 | 3 | 6 | 360 | 58.0191 | 20886.876
67 | Demin forwarding pumps |  |  | 1 | 25000 | 25000 | 750 | 750 | 10 | 3 | 4 | 120 | 58.0191 | 6962.292
68 | Demin Filter Skid |  |  | 2 | 60000 | 120000 | 3600 | 7200 | 10 | 3 | 4 | 240 | 58.0191 | 13924.584
69 | Demin Water Tank, SS 300M gal |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
70
71 | Waste Water and Oil Storage and Transfer
72 | Oily Water Separator |  |  | 1 | 55000 | 55000 | 4000 | 4000 | 10 | 4 | 3 | 120 | 58.0191 | 6962.292
73 | Oily Waste Tank 10000 gal |  |  | 1 | 15000 | 15000 | 450 | 450 | 10 | 2 | 3 | 60 | 58.0191 | 3481.146
74 | Waste Water Tank 10000 gal |  |  | 1 | 15000 | 15000 | 450 | 450 | 10 | 2 | 3 | 60 | 58.0191 | 3481.146
75 | Waste Oil and Water forwarding pumps w/ skid |  |  | 2 | 10000 | 20000 | 600 | 1200 | 10 | 2 | 3 | 120 | 58.0191 | 6962.292
76 | Waste Sludge Tank with forwarding pump |  |  | 1 | 15000 | 15000 | 1500 | 1500 | 10 | 4 | 4 | 160 | 58.0191 | 9283.056
77 | Fire Control Systems
78 | Fire Water Pump Skids (Diesel / Electric) |  |  | 1 | 550000 | 550000 | 16500 | 16500 | 10 | 4 | 8 | 320 | 58.0191 | 18566.112
79 | Fire Water System, valves, hydrants, monitors |  |  | 1 | 125000 | 125000 | 3750 | 3750 | 10 | 6 | 12 | 720 | 58.0191 | 41773.752
80 | Fire Water System, PM/CM/TA/commissioning |  |  | Qty: 1; Unit: 120000; Total: 120000; Unit: 0; Frt: 0
81 | Storm Water System
82 | HDPE Pipe - (__)" |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
83 | HDPE Pipe - (__)" |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
84 | Sump Pumps |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
85
86 | Other Systems
87 | Instrument Air Compressor Package, net (___) scfm |  |  | 1 | 72000 | 72000 | 3000 | 3000 | 10 | 3 | 4 | 120 | 58.0191 | 6962.292
88 | Potable Water System |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
89 | Anti-Icing Ducting |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
90 | Emergency Generator |  |  | 1 | 250000 | 250000 | 7500 | 7500 | 10 | 4 | 6 | 240 | 58.0191 | 13924.584
91 |  |  |  | Hours: 10
92
93 |  |  | Total Cost | Total: 4644; Frt: 266.32; Qty: 15590
94 |  |  |  | Total: 904.5178
[9 empty] | Total Manhours |  |  | 15590
[9 empty] | Times Prod Factor |  | 1.8 | 28062 | 58.0191 | 1628.132
95 | BOP Pipe, Valves and Fittings Labor |  |  | 1 | 900000 | 900000 | 27000 | 27000 | 10 | 15 | 130 | 19500 | 58.0191 | 1131372.45
96 |  |  | Total Cost | Total: 900; Frt: 27; Qty: 19500; Total: 1131372.45
97
98 |  |  |  | Hours: Total Manhours; Qty: 19500
99 |  |  |  | Hours: Times Prod Factor; Qty: 1.8; Qty: 35100; Rate: 58.0191; Total: 2036.4704
Price per hour based with all labor burdens as follows:
[8 empty] | Local Hrly Cost |  | 30
[8 empty] | Fringes |  | 2.5
[8 empty] | Small Tools |  | 1.5
[8 empty] | Labor Burden 35% |  | 10.5
44.5
[8 empty] | Contr G&A 8% |  | 3.56
[8 empty] | Contr Mark up 15% |  | 6.675
54.735
[7 empty] | 45 | Hour Work Week = |  | 58.0191
Work Week Hours Multiplier
[7 empty] | 45 | 50 | 60
[7 empty] | 1.06 | 1.1 | 1.17
Note on K127: Insert Weekly M/hrs Here: Weekly M/hrs automatically calculated hrs/day.
Note on N119: Insert Rate Here:

## 410, 430, 450 & 460 Electrical
ELECTRICAL EQUIPMENT and Labor
(1,000's)
410, 430, 450 & 460
Project Name: |  | Barinas I Power Plant | [11 empty] | Date: |  | 2011-10-26
Customer: |  | PDVSA | [11 empty] | Quote No: |  | T 1003
Location: |  | Barinas, Venn | [11 empty] | Est By: |  | RHL-civil by Derwick-as sold
Bid Due Date:
Item |  | Description |  | Mfgr. | Location | Qty | Unit | Total | Unit | Frt | Hours | Qty | Qty | Qty | Rate | Total
No. | [6 empty] | Price | Price | Frt Pr | Price | (day) | (men) | (days) | (mhrs) | (hour) | Labor
1 | Power Island Equipment | [7 empty] | 3% |  | 10
2 | Gas Turbine Generator |  |  |  |  | 2 |  |  | 0 |  | 10 | 9 | 35 | 6300 | 58.0191 | 365520.33
3 | HRSG |  |  |  |  | 0 |  |  | 0 |  | 10 | 0 | 0 | 0 | 58.0191 | 0
4 | SCR |  |  |  |  | 0 |  |  | 0 |  | 10 | 0 | 0 | 0 | 58.0191 | 0
5 | STG |  |  |  |  | 0 |  |  | 0 |  | 10 | 0 | 0 | 0 | 58.0191 | 0
6 | STG Cooling Tower |  |  |  |  | 0 |  |  | 0 |  | 10 | 0 | 0 | 0 | 58.0191 | 0
7 | Emergency Generator |  |  |  |  | 1 |  |  | 0 |  | 10 | 4 | 5 | 200 | 58.0191 | 11603.82
8 | Water Treatment Package |  |  |  |  | 1 |  |  | 0 |  | 10 | 4 | 7 | 280 | 58.0191 | 16245.348
9 | [13 empty] | 0 | 58.0191 | 0
10 | 15KV | [13 empty] | 58.0191
11 | Generator Breaker(s) |  |  |  |  | 2 | 155000 | 310000 | 9300 | 18600 | 10 | 4 | 5 | 400 | 58.0191 | 23207.64
12 | Distribution Breaker(s) |  |  |  |  | 2 | 60000 | 120000 | 3600 | 7200 | 10 | 4 | 4 | 320 | 58.0191 | 18566.112
13 | Fused Disconnect(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 3 | 4 | 0 | 58.0191 | 0
14 | Bus Duct Cable |  |  |  |  | 2 | 50000 | 100000 | 3000 | 6000 | 10 | 3 | 4 | 240 | 58.0191 | 13924.584
15 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 4 | 0 | 58.0191 | 0
16 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 6 | 0 | 58.0191 | 0
17 | 5KV | [13 empty] | 58.0191
18 | Distribution Breaker(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 58.0191 | 0
19 | Fused Disconnect(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 6 | 0 | 58.0191 | 0
20 | MCC's |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 1 | 0 | 58.0191 | 0
21 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 6 | 0 | 58.0191 | 0
22 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 58.0191 | 0
23 | 600V | [13 empty] | 58.0191
24 | Distribution Panel(s) |  |  |  |  | 1 | 105000 | 105000 | 3150 | 3150 | 10 | 2 | 5 | 100 | 58.0191 | 5801.91
25 | GTG MCC(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 58.0191 | 0
26 | HRSG MCC(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 4 | 0 | 58.0191 | 0
27 | STG MCC(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 58.0191 | 0
28 | BOP MCC(s) |  |  |  |  | 1 | 25000 | 25000 | 750 | 750 | 10 | 2 | 3 | 60 | 58.0191 | 3481.146
29 | Water Treatment MCC(s) |  |  |  |  | 1 | 10000 | 10000 | 300 | 300 | 10 | 2 | 2 | 40 | 58.0191 | 2320.764
30 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 8 | 0 | 58.0191 | 0
31 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 58.0191 | 0
32 | Aux Transformer(s) | [13 empty] | 58.0191
33 | 15/5KV ___________ MVA |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 58.0191 | 0
34 | 15/600V ___________ MVA |  |  |  |  | 2 | 75000 | 150000 | 5000 | 10000 | 10 | 3 | 5 | 300 | 58.0191 | 17405.73
35 | 600/120/208V ________ KVA |  |  |  |  | 1 | 5000 | 5000 | 150 | 150 | 10 | 3 | 3 | 90 | 58.0191 | 5221.719
36 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
37 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
38 | Area Lighting | [13 empty] | 58.0191
39 | Poles _______ High |  |  |  |  | 8 | 1500 | 12000 | 360 | 2880 | 10 | 2 | 1 | 160 | 58.0191 | 9283.056
40 | Floodlights _______ Watts |  |  |  |  | 32 | 600 | 19200 | 576 | 18432 | 10 | 2 | 0.2 | 128 | 58.0191 | 7426.4448
41 | [5 empty] | 0 | 0 | 0 |  | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
42 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 60 | 0 | 58.0191 | 0
43 | Other Systems | [13 empty] | 58.0191
44 | UPS |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 10 | 0 | 58.0191 | 0
45 | DC |  |  |  |  | 0 | 0 | 0 |  | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
46 | Cathodic Protection |  |  |  |  | 2 | 20000 | 40000 | 1200 | 2400 | 10 | 4 | 8 | 640 | 58.0191 | 37132.224
47 | Lightning Protection |  |  |  |  | 2 | 15000 | 30000 | 900 | 1800 | 10 | 4 | 6 | 480 | 58.0191 | 27849.168
48 | [11 empty] | 0 | 0 | 0 | 58.0191 | 0
49 | [14 empty] | 58.0191
50 | Temporary Electric |  |  |  |  | 1 | 40000 | 40000 | 1200 | 1200 | 10 | 2 | 45 | 900 | 58.0191 | 52217.19
51 | Electrical Control Module |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
52 | [6 empty] | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
53 | [6 empty] | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
54 | [6 empty] | 0 | 0 |  | 0 | 10 | 0 | 0 | 0 | 58.0191 | 0
55 |  |  | Total Cost of Electrical Equipment |  |  |  |  | 966.2 |  | 72.862 |  |  |  | 10638 |  | 617.2072
[12 empty] | Productivity | 1.8 | 19148.4 | 58.0191 | 1110.9729
56 | Cable Tray, Conduit, & Cable |  |  |  |  | 1 | 900000 | 900000 | 27000 | 27000 | 10 | 12 | 130 | 15600 | 58.0191 | 905097.96
57 |  |  | Total Cost of Electrical Equipment |  |  |  |  | 900 |  | 27 |  |  |  | 15600 |  | 905.098
58 | [10 empty] | Total Manhours |  |  | 15600
59 | [10 empty] | Times Prod Factor |  | 1.8 | 28080 | 58.0191 | 1629.1763
Price per hour based with all labor burdens as follows:
[13 empty] | Local Hrly Cost |  | 30
[13 empty] | Fringes |  | 2.5
[13 empty] | Small Tools |  | 1.5
[13 empty] | Labor Burden 35% |  | 10.5
44.5
[13 empty] | Contr G&A 8% |  | 3.56
[13 empty] | Contr Mark up 15% |  | 6.675
54.735
[12 empty] | 45 | Hour Work Week = |  | 58.0191
Work Week Hours Multiplier
[12 empty] | 45 | 50 | 60
[12 empty] | 1.06 | 1.1 | 1.17
Note on N87: Insert Weekly M/hrs Here: Automatically calculates hrs/day.
Note on Q79: Insert Rate Here:

## 420 & 440 Substation
SUBSTATION EQUIPMENT and Labor
(1,000's)
Project Name: |  | Barinas I Power Plant | [12 empty] | Date: | 2011-10-26
Customer: |  | PDVSA | [12 empty] | Quote No: | T 1003
Location: |  | Barinas, Venn | [12 empty] | Est By:
Bid Due Date:
Item |  | Description |  | Mfgr | Loc | Qty | Unit | Total | Unit | Frt | Hours | Qty | Qty | Qty | Rate | Total
No. | [6 empty] | Price | Price | Frt Pr | Price | (day) | (men) | (days) | (mhrs) | (hour) | Labor
1 |  |  |  | Unit: 3%; Hours: 10
2 | Main Power Transformer _115 KV, _75_ MVA |  |  |  |  | 2 | 0 | 0 | 0 | 0 | 10 | 4 | 10 | 800 | 58.0191 | 46415.28
3 | SF6 Circuit Breaker(s) ____ KV |  |  |  |  | 2 | 60000 | 120000 | 3600 | 7200 | 10 | 2 | 7 | 280 | 58.0191 | 16245.348
4 | Disconnect Switches ______ KV |  |  |  |  | 2 | 25000 | 50000 | 1500 | 3000 | 10 | 2 | 5 | 200 | 58.0191 | 11603.82
5 | Station Post Insulators ____ KV |  |  |  |  | 6 | 550 | 3300 | 99 | 594 | 10 | 2 | 0.05 | 6 | 58.0191 | 348.1146
6 | Insulator Stanchons ______ High |  |  |  |  | 6 | 550 | 3300 | 99 | 594 | 10 | 1 | 0.5 | 30 | 58.0191 | 1740.573
7 | Insulator Stanchons ______ High |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 0.4 | 0 | 58.0191 | 0
8 | Dead End Tower(s) |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 6 | 5 | 0 | 58.0191 | 0
9 | Alum Bus ______ Dia Lot of Bus and fittings |  |  |  |  | 1 | 125000 | 125000 | 3750 | 3750 | 10 | 6 | 30 | 1800 | 58.0191 | 104434.38
10 | Alum Bus Conn's |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 0.1 | 0 | 58.0191 | 0
11 | Alum Bus End Plugs _____ Dia |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 0.05 | 0 | 58.0191 | 0
12 | Alum Bus Support Clamps |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 0.1 | 0 | 58.0191 | 0
13 | Alum Bus "V" Conn's |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 0.08 | 0 | 58.0191 | 0
14 | Static Wire Poles, ____ High |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 1 | 0 | 58.0191 | 0
15 | Area Lighting Poles, ____ High |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 1 | 0 | 58.0191 | 0
16 | Flood Lights, ______ Watts |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 58.0191 | 0
17 | #4/0 Grounding Conductor |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 0.03 | 0 | 58.0191 | 0
18 | 3/4"x10'-0" Ground Rods & Clamps |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 0.04 | 0 | 58.0191 | 0
19 | #90 Cadweld Shots |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 0.3 | 0 | 58.0191 | 0
20 | Metering CT's & CPT's |  |  |  |  | 2 | 35000 | 70000 | 2100 | 4200 | 10 | 2 | 3 | 120 | 58.0191 | 6962.292 | 0
21 | Station Metering w/ In & Out Capabilities |  |  |  |  | 1 | 50000 | 50000 | 1500 | 1500 | 10 | 2 | 5 | 100 | 58.0191 | 5801.91
22 | Station Protective Relay(s) |  |  |  |  | 1 | 50000 | 50000 | 1500 | 1500 | 10 | 2 | 5 | 100 | 58.0191 | 5801.91
23 | Station RTU |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 5 | 0 | 58.0191 | 0
24 | 125V DC System |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 58.0191 | 0
25 | Transmission Line Poles |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 6 | 2 | 0 | 58.0191 | 0
26 | Transmission Line Strain Insulators |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 1 | 0 | 0 | 58.0191 | 0 | 0
27 | Cable Bus, Type _____, Size _____ |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 6 | 6 | 0 | 58.0191 | 0
28 | Main Power Transformer Oil, ______ Gal |  |  |  |  | 2 | 55000 | 110000 | 3300 | 6600 | 10 | 2 | 5 | 200 | 58.0191 | 11603.82
29 | Main Power Transformer Dress Out & Test |  |  |  |  | 2 | 50000 | 100000 | 3000 | 6000 | 10 | 2 | 0 | 0 | 58.0191 | 0
30 | Fiber Optic Cable w/ Messenger Cable |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 4 | 5 | 0 | 58.0191 | 0 | 0
31 | Fiber Optic Cable Fittings & Terminations |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 10 | 2 | 2 | 0 | 58.0191 | 0
32 |  |  |  | Hours: 10; Rate: 58.0191
33 |  |  |  | Hours: 10; Rate: 58.0191
34 | Final TSD scope adder negotiation |  |  | Total: 520000; Hours: 10; Rate: 58.0191
35 |  |  |  | Hours: 10; Rate: 58.0191; Total: 0
36 |  |  | Total Cost of Substation Equipment | Total: 1201.6; Frt: 34.938; Qty: 3636; Total: 210.9574
[12 empty] | Total Hours |  | 3636
[12 empty] | Prod Factor | 1.8 | 6544.8 | 58.0191 | 379.7234
Price per hour based with all labor burdens as follows:
[13 empty] | Local Hrly Cost |  | 30
[13 empty] | Fringes |  | 2.5
[13 empty] | Small Tools |  | 1.5
[13 empty] | Labor Burden 35% |  | 10.5
44.5
[13 empty] | Contr G&A 8% |  | 3.56
[13 empty] | Contr Mark up 15% |  | 6.675
54.735
[12 empty] | 45 | Hour Work Week = |  | 58.0191
Work Week Hours Multiplier
[12 empty] | 45 | 50 | 60
[12 empty] | 1.06 | 1.1 | 1.17
Note on N61: Insert Weekly M/hrs Here: Automatically calculates hrs/day.
Note on Q53: Insert Rate Here:

## 520 & 530 Instrumentation
PLANT INSTRUMENTATION
(1,000's)
520 &530
Project Name: |  | Barinas I Power Plant | [8 empty] | Date: | 2011-10-26
Customer: |  | PDVSA | [8 empty] | Quote No: | T 1003
Location: |  | Barinas, Venn | [8 empty] | Est By: | RHL-civil by Derwick-as sold
Bid Due Date:
Item |  | Description |  | Qty | Unit | Total | Hours | Qty | Qty | Qty | Rate | Total
No. |  |  |  | GTG's | Cost | Cost | (day) | (men) | (days) | (mhrs) | (hour) | Labor
1 |  |  |  | Hours: 10
2 | Instrumentation for GTG |  |  | 2 | 35000 | 70000 | 10 | 2 | 10 | 400 | 58.0191 | 23207.64
3 |  |  |  | Hours: 10; Rate: 58.0191; Total: 0
4 | Instrumentation for SCR |  |  | 0 | 0 | 0 | 10 | 4 | 15 | 0 | 58.0191 | 0
5 |  |  |  | Hours: 10; Rate: 58.0191
6 | Instrumentation for HRSG |  |  | 0 | 0 | 0 | 10 | 4 | 15 | 0 | 58.0191 | 0
7 |  |  |  | Hours: 10; Rate: 58.0191
8 | Instrumentation for Injection Water Treatment |  |  | 1 | 25000 | 25000 | 10 | 2 | 10 | 200 | 58.0191 | 11603.82
9 |  |  |  | Hours: 10; Rate: 58.0191
10 | Instrumentation for Waste Water Treatment |  |  | 0 | 0 | 0 | 10 | 2 | 10 | 0 | 58.0191 | 0
11 |  |  |  | Hours: 10; Rate: 58.0191
12 | Instrumentation for DFO Treatment |  |  | 1 | 30000 | 30000 | 10 | 4 | 5 | 200 | 58.0191 | 11603.82
13 |  |  |  | Hours: 10; Rate: 58.0191
14 | Labor to Install CEMS |  |  | 0 | 0 | 0 | 10 | 4 | 5 | 0 | 58.0191 | 0
15 |  |  |  | Hours: 10; Rate: 58.0191
16 |  |  |  | Hours: 10; Rate: 58.0191
17 |  |  |  | Hours: 10; Rate: 58.0191
18 |  |  |  | Hours: 10; Rate: 58.0191
19 |  |  |  | Hours: 10; Rate: 58.0191
20 |  |  |  | Hours: 10; Rate: 58.0191
21 |  |  |  | Hours: 10; Rate: 58.0191
22 |  |  |  | Hours: 10; Rate: 58.0191
23 |  |  | Total Cost of Plant Instrumentation | Total: 125; Qty: 800; Total: 46.4153
[8 empty] | Total Hours |  | 800
[8 empty] | Prod Factor | 1.8 | 1440 | 58.0191 | 83.5475
Price per hour based with all labor burdens as follows:
[9 empty] | Local Hrly Cost |  | 30
[9 empty] | Fringes |  | 2.5
[9 empty] | Small Tools |  | 1.5
[9 empty] | Labor Burden 35% |  | 10.5
44.5
[9 empty] | Contr G&A 8% |  | 3.56
[9 empty] | Contr Mark up 15% |  | 6.675
54.735
[8 empty] | 45 | Hour Work Week = |  | 58.0191
Work Week Hours Multiplier
[8 empty] | 45 | 50 | 60
[8 empty] | 1.06 | 1.1 | 1.17
Note on L50: Insert Weekly M/hrs Here: Automatically calculates hr/day.
Note on O42: Inset Rate Here:

## 610, 620, 630 & 640 DCS
DCS
|  |  |  | (1,000's) |  |  |  | 610, 620, 630 & 640
Project Name: |  | Barinas I Power Plant |  |  |  |  | Date: | 2011-10-26
Customer: |  | PDVSA |  |  |  |  | Quote No: | T 1003
Location: |  | Barinas, Venn |  |  |  |  | Est By: | RHL-civil by Derwick-as sold
Bid Due Date:
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [6 empty] | Cost | Cost
1
2 | DCS Hardware / Software |  |  |  |  | 1 | 430000 | 430000
3 | PW Remote HMI |  |  |  |  | 2 | 75000 | 150000
4 | Lot of Misc interconnecting cables etc. |  |  |  |  | 2 | 15000 | 30000
5
6 | Documentation |  |  |  |  | 1 | 75000 | 75000
7
8 |  |  |  |  | Total DCS |  |  | 685
9
10 | PBX Communications System |  |  |  |  | 1 | 15000 | 15
11
12 | Loud Speaker System |  |  |  |  | 1 | 15000 | 15
13
14 | TV / Security System |  |  |  |  | 0 | 20000 | 0
15
16
17
[7 empty] | taxable | 460030

## 700 Erection
PLANT ERECTION
(1,000's)
700
Project Name: |  | Barinas I Power Plant | [6 empty] | Date: | 2011-10-26
Customer: |  | PDVSA | [6 empty] | Quote No: | T 1003
Location: |  | Barinas, Venn | [6 empty] | Est By: | RHL-civil by Derwick-as sold
Bid Due Date:
Item |  | Description |  | No | Hours | Qty | Qty | Qty | Rate | Total
No. |  |  |  | Units | (day) | (men) | (days) | (mhrs) | (hour) | Labor
1 |  |  |  |  | 10
2 | GTG Erection |  |  | 2 | 10 | 12 | 35 | 8400 | 58.0191 | 487360.44
3 |  |  |  |  | 10 |  |  |  | 58.0191
4 | HRSG Erection |  |  | 0 | 10 | 10 | 60 | 0 | 58.0191 | 0
5 |  |  |  |  | 10 |  |  |  | 58.0191
6 | SCR Erection |  |  | 0 | 10 | 10 | 60 | 0 | 58.0191 | 0
7 |  |  |  |  | 10 |  |  |  | 58.0191
8 | Water Treatment and FW Systems |  |  | 1 | 10 | 4 | 20 | 800 | 58.0191 | 46415.28
9 |  |  |  |  | 10 |  |  |  | 58.0191
10 | DFO Treatment System |  |  | 1 | 10 | 5 | 20 | 1000 | 58.0191 | 58019.1
11 |  |  |  |  | 10 |  |  |  | 58.0191
12 | BOP Equip Erection |  |  | 1 | 10 | 6 | 20 | 1200 | 58.0191 | 69622.92
13 |  |  |  |  | 10 |  |  |  | 58.0191
14 | Gas Compressor Erection |  |  | 0 | 10 | 6 | 5 | 0 | 58.0191 | 0
15 |  |  |  |  | 10 |  |  |  | 58.0191
16 | Evap Cooling Erection |  |  | 0 | 10 | 4 | 4 | 0 | 58.0191 | 0
17 |  |  |  |  | 10 |  |  |  | 58.0191
18 | Fire Water Pump Skid |  |  | 1 | 10 | 4 | 15 | 600 | 58.0191 | 34811.46
19 |  |  |  |  | 10 |  |  |  | 58.0191
20 | Diesel Engine Removal |  |  | 0 | 10 | 6 | 5 | 0 | 58.0191 | 0
21 |  |  |  |  | 10 |  |  |  | 58.0191
22 | Diesel Engine Piping Removal "Lot" |  |  | 0 | 10 | 6 | 15 | 0 | 58.0191 | 0
23 |  |  |  |  | 10 |  |  |  | 58.0191
24 |  |  |  |  | 10 |  |  |  | 58.0191
25 |  |  | Total Cost of Plant Erection |  |  |  |  | 12000 |  | 696.2292
[6 empty] | Total Hours |  | 12000
[6 empty] | Prod Factor | 1.8 | 21600 | 58.0191 | 1253.2126
Price per hour based with all labor burdens as follows:
[7 empty] | Local Hrly Cost |  | 30
[7 empty] | Fringes |  | 2.5
[7 empty] | Small Tools |  | 1.5
[7 empty] | Labor Burden 35% |  | 10.5
44.5
[7 empty] | Contr G&A 8% |  | 3.56
[7 empty] | Contr Mark up 15% |  | 6.675
54.735
[6 empty] | 45 | Hour Work Week = |  | 58.0191
Work Week Hours Multiplier
[6 empty] | 45 | 50 | 60
[6 empty] | 1.06 | 1.1 | 1.17
Note on J52: Insert Weekly M/hrs Here: Automatically calculates hr/day.
Note on M44: Insert Rate Here:

## 800 Equip rent
EQUIPMENT RENTAL
[5 empty] | (1,000's) |  |  |  |  | 800
Project Name: |  | Barinas I Power Plant | [6 empty] | Date: | 2011-10-26
Customer: |  | PDVSA | [6 empty] | Quote No: | T 1003
Location: |  | Barinas, Venn | [6 empty] | Est By: | RHL-civil by Derwick-as sold
Bid Due Date:
Item |  | Description |  |  |  | No. | Days | Total | Cost | Total
No. | [5 empty] | Units | Unit | Days | Per Day | Cost
1 | GTG Equip Rental per ea GTG
2 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 2 | 8 | 16 | 8000 | 128000
3 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
4 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 2 | 35 | 70 | 4000 | 280000
5 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
6 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
7 | 2 ea Fork Lifts |  |  |  |  | 0 | 0 | 0 | 70 | 0
8 | 1 ea Man Lift |  |  |  |  | 2 | 35 | 70 | 100 | 7000
9 | 2 ea Welders |  |  |  |  | 5 | 35 | 175 | 100 | 17500
10
11 | HRSG Erection
12 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
13 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
14 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 2000 | 0
15 | 1 ea 40 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
16 | 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
17 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
18 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
19
20 | SCR/CO
21 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
22 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
23 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 2000 | 0
24 | 1 ea 40 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
25 | 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
26 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
27 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
28
29 | STG
30 | 1 ea 200 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
31 | 1 ea 100 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3500 | 0
32 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1000 | 0
33 | 2 ea Man Lifts |  |  |  |  | 0 | 0 | 0 | 80 | 0
34 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
35 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
36
37 | Diesel Engine Removal
38 | 75 Ton Crane |  |  |  |  | 0 | 1 | 0 | 2000 | 0
39 | 40 Ton Crane at unload site |  |  |  |  | 0 | 1 | 0 | 1500 | 0
40 | Trucks to unload site |  |  |  |  | 0 | 1 | 0 | 4000 | 0
41
42 | Fuel Gas Compressor Rental per Compr Skid
43 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
44 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 1500 | 0
45
46 | BOP Equip Rental per ea GTG
47 | 1 ea 300 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 4000 | 0
48 | 1 ea 150 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3000 | 0
49 | 1 ea 50 Ton Crane w/ operator |  |  |  |  | 1 | 25 | 25 | 4000 | 100000
50 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 1 | 125 | 125 | 2500 | 312500
51 | 2 ea Fork Lifts |  |  |  |  | 1 | 125 | 125 | 100 | 12500
52 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
53 | 2 ea Pick ups |  |  |  |  | 2 | 125 | 250 | 80 | 20000
54 | 1 ea Front End Loader / Back Hoe |  |  |  |  | 1 | 125 | 125 | 70 | 8750
55
56 | Substation Equip Rental
57 | 1 ea 200 Ton Crane w/ operator |  |  |  |  | 2 | 5 | 10 | 4000 | 40000
58 | 1 ea 100 Ton Crane w/ operator |  |  |  |  | 0 | 0 | 0 | 3500 | 0
59 | 1 ea 20 Ton Crane w/ operator |  |  |  |  | 1 | 30 | 30 | 2000 | 60000
60 | 2 ea Man Lifts |  |  |  |  | 1 | 25 | 25 | 80 | 2000
61 | 2 ea Sky Tracs |  |  |  |  | 0 | 0 | 0 | 70 | 0
62 | 5 ea Welders |  |  |  |  | 0 | 0 | 0 | 80 | 0
63
64
65
66
67
68 |  |  | Total Cost of Plant Equip Rental |  |  |  |  | 1021 |  | 988.25

## 900 Paint
PLANT PAINTING
[5 empty] | (1,000's) |  |  | 900
Project Name: |  | Barinas I Power Plant |  |  |  |  | Date: | 2011-10-26
Customer: |  | PDVSA |  |  |  |  | Quote No: | T 1003
Location: |  | Barinas, Venn |  |  |  |  | Est By: | RHL-civil by Derwick-as sold
Bid Due Date:
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [5 empty] | Units | Cost | Cost
1
2 | Paint for GTG |  |  |  |  | 2 | 75000 | 150000
3
4 | Paint for STG and Auxiliaries |  |  |  |  | 0 | 60000 | 0
5
6 | Paint for SCR w/ Pipe Racks |  |  |  |  | 0 | 135000 | 0
7
8 | Paint for Pipe Rack etc. |  |  |  |  | 1 | 40000 | 40000
9
10 | Paint for BOP Equipment |  |  |  |  | 1 | 65000 | 65000
11
12 | Paint for Gas Compressor |  |  |  |  | 0 | 15000 | 0
13
14 | Paint for Water Treatment |  |  |  |  | 1 | 15000 | 15000
15
16 | Paint for DFO Treatment |  |  |  |  | 1 | 15000 | 15000
17
18 | Paint for HRSG |  |  |  |  | 0 | 95000 | 0
19
20
21
22
23
24
25
26
27
28
29
30 |  |  | Total Cost of Plant Painting |  |  |  |  | 285

## 1000 Transportation
PLANT TRANSPORTATION
[5 empty] | (1,000's) |  |  | 1000
Project Name: |  | Barinas I Power Plant |  |  |  |  | Date: | 2011-10-26
Customer: |  | PDVSA |  |  |  |  | Quote No: | T 1003
Location: |  | Barinas, Venn |  |  |  |  | Est By: | RHL-civil by Derwick-as sold
Bid Due Date:
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [5 empty] | Units | Cost | Cost
1
2 | Transportation of Plant Major Mechanical Equip |  |  |  |  | 1 | 266.32 | 266.32
3
4 | Transportation of Plant Major Electrical Equip |  |  |  |  | 1 | 72.862 | 72.862
5
6 | Transportation Substation Equip |  |  |  |  | 1 | 34.938 | 34.938
7
8 | Transportation of GTG
9
10 | Transportation of SCR
11
12 | Transportation of HRSG
13
14 | Transportation of STG
15
16 | Pipe, Valves & Fittings |  |  |  |  | 1 | 27 | 27
17
18 | Conduit, Cable & Wire |  |  |  |  | 1 | 27 | 27
19
20 | Buildings |  |  |  |  | 1 | 30 | 30
21
22 | Contingency |  |  |  |  | 1 | 150 | 150
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Plant Transportation |  |  |  |  | 608.12

## 1100 Site Costs
SITE COSTS
[5 empty] | (1,000's) |  |  |  |  | 1100
Project Name: |  | Barinas I Power Plant | [6 empty] | Date: | 2011-10-26
Customer: |  | PDVSA | [6 empty] | Quote No: | T 1003
Location: |  | Barinas, Venn | [6 empty] | Est By: | RHL-civil by Derwick-as sold
Bid Due Date:
Item |  | Description |  |  |  | No. | No. | Cost | Total | Total
No. | [5 empty] | Units | Mos | Per Mo | Mo Cost | Cost
1 | Monthly Site Costs
2 | Office Trailers |  |  |  |  | 6 | 12 | 2500 | 180000
3 | Porta Potties |  |  |  |  | 6 | 12 | 150 | 10800
4 | Water and Ice |  |  |  |  | 5 | 12 | 500 | 30000
5 | Fed X |  |  |  |  | 1 | 12 | 500 | 6000
6 | Telephone |  |  |  |  | 1 | 12 | 2500 | 30000
7 | Office Supplies |  |  |  |  | 1 | 12 | 1000 | 12000
8 | [6 empty] | 12
9 | Diesel Fuel for Power Generator and Welders |  |  |  |  | 1 | 12 | 3000 | 36000
10 | Misc Items |  |  |  |  | 1 | 12 | 3000 | 36000
11 |  |  | Total Monthly Cost | [5 empty] | 340800
12
13
14
15
16
17
18 | Monthly Site Costs | [5 empty] | 1 | 340800 |  | 340800
19 | One Time Costs
20 | 500 KW Diesel Generator w/ Dist Equip | [8 empty] | 200000
21 | Cad Station | [8 empty] | 5000
22 | Computers | [8 empty] | 10000
23 | Telephone System and Satalite Dish | [8 empty] | 15000
24 | Plotter | [8 empty] | 0
25 | Fax Machine and Printers | [8 empty] | 3000
26 | Misc equip | [8 empty] | 50000
27 | Signs | [8 empty] | 0
28
29
30
31
32 | Total Project Cost = Cost per Month Times Number of Mos
33 | Plus the Project One Time Costs.
34
35 |  |  | Total Cost of Project Site Costs | [6 empty] | 623.8

## 1200 Engineering
ENGINEERING
[5 empty] | (1,000's) |  |  | 1200
Project Name: |  | Barinas I Power Plant |  |  |  |  | Date: | 2011-10-26
Customer: |  | PDVSA |  |  |  |  | Quote No: | T 1003
Location: |  | Barinas, Venn |  |  |  |  | Est By: | RHL-civil by Derwick-as sold
Bid Due Date:
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [5 empty] | Units | Cost | Cost
1
2 | Conceptual Engineering |  |  |  |  | 1 | 50000 | 50000
3
4 | Detailed Engineering per GTG |  |  |  |  | 2.5 | 390000 | 975000
5
6 | Detailed Engineering per HRSG |  |  |  |  | 0 | 0 | 0
7
8 | Detailed Engineering per STG |  |  |  |  | 0 | 0 | 0
9
10 | Detailed Engineering for DFO Treatment |  |  |  |  | 1.25 | 40000 | 50000
11
12 | Detailed Engineering per Water Treatment |  |  |  |  | 1.25 | 40000 | 50000
13
14 | Detailed Engineering per Structural Steel |  |  |  |  | 1 | 80000 | 80000
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33 |  |  | Total Cost of Engineering |  |  |  |  | 1205

## 1210 Local Engineering
LOCAL ENGINEERING
[5 empty] | (1,000's) |  |  | 1210
Project Name: |  | Barinas I Power Plant |  |  |  |  | Date: | 2011-10-26
Customer: |  | PDVSA |  |  |  |  | Quote No: | T 1003
Location: |  | Barinas, Venn |  |  |  |  | Est By: | RHL-civil by Derwick-as sold
Bid Due Date:
Item |  | Description |  |  |  | Qty | Unit | Total
No. | [5 empty] | Units | Cost | Cost
1
2 | Soils & Environmental Eng |  |  |  |  | 1 | 20000 | 20000
3
4 | Civil Engineer |  |  |  |  | 5 | 20000 | 100000
5
6 | Mechanical Engineer |  |  |  |  | 6 | 20000 | 120000
7
8 | Electrical Engineer |  |  |  |  | 6 | 20000 | 120000
9
10 | Other |  |  |  |  | 0 | 0 | 0
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40 |  |  | Total Cost of Local Engineering |  |  |  |  | 360

## 1310 & 1320 PM-CM-Insp
PROJECT MANAGEMENT LABOR
|  |  |  | (1,000's) |  |  |  | 1310 & 1320
Project Name: |  | Barinas I Power Plant |  |  |  |  | Date: | 2011-10-26
Customer: |  | PDVSA |  |  |  |  | Quote No: | T 1003
Location: |  | Barinas, Venn |  |  |  |  | Est By: | RHL-civil by Derwick-as sold
Bid Due Date:
Item |  | Description |  |  |  | No. | Cost | Total
No. | [5 empty] | Mos | Per Mo | Cost
Home Office
1 | Project Mgr Months on Project |  |  |  |  | 12 | 16000 | 192000
2 | Admin Mgr Months on Project |  |  |  |  | 12 | 6000 | 72000
3 | Scheduler |  |  |  |  | 10 | 8000 | 80000
4 | Purchasing Agent |  |  |  |  | 4 | 8000 | 32000
5 | Expediter |  |  |  |  | 6 | 5000 | 30000
6 | Home Office Logistic Coordinator |  |  |  |  | 12 | 9000 | 108000
7
8
9 | [6 empty] | 514000
10
11
12
13
14
15
16 | Site Construction
17 | Secretary |  |  |  |  | 12 | 4000 | 48000
18 | Construction Mngr |  |  |  |  | 12 | 16000 | 192000
19 | Contract Cost Admin |  |  |  |  | 0 | 10000 | 0
20 | Scheduler |  |  |  |  | 12 | 8000 | 96000
21 | Mechanical Supervisor |  |  |  |  | 12 | 14000 | 168000
22 | Electrical Supervisor |  |  |  |  | 12 | 14000 | 168000
23 | Civil Supervisor |  |  |  |  | 12 | 14000 | 168000
24 | Clerks |  |  |  |  | 12 | 5000 | 60000
25 | Warehousemen |  |  |  |  | 12 | 3000 | 36000
26 | Draftsman |  |  |  |  | 5 | 8000 | 40000
27 | Security |  |  |  |  | 12 | 14000 | 168000
28 | Safety |  |  |  |  | 12 | 12000 | 144000
29 | QA/QC Mngr |  |  |  |  | 12 | 14000 | 168000
30
31
32 | [6 empty] | 1456000
33
34 | Commissioning Techs __ ea __ mos x __ |  |  |  |  | 6 | 14000 | 84000
35
36
37
38 | Training |  |  |  |  | 0 | 0 | 0
39
40 |  |  |  |  | Total Project & Construction Management |  |  | 2054
41
42
43
44
45 | Inspectors
46 | Civil - Structual __ ea ___ mos |  |  |  |  | 8 | 11500 | 92000
47 | Mechanical __ ea ___ mos |  |  |  |  | 8 | 11500 | 92000
48 | Electrical __ ea ___ mos |  |  |  |  | 8 | 11500 | 92000
49 | Welder __ ea ___ mos | __ ea ___ mos |  |  |  | 8 | 11500 | 92000
50
51 |  |  |  |  | Total Inspectors |  |  | 368000
52

## 1400 & 1410 Travel & Perdiem
PROJECT MGT TVL AND PER DIEM
|  |  |  | (1,000's) |  |  |  | 1400 & 1410
Project Name: |  | Barinas I Power Plant |  |  |  |  | Date: | 2011-10-26
Customer: |  | PDVSA |  |  |  |  | Quote No: | T 1003
Location: |  | Barinas, Venn |  |  |  |  | Est By: | RHL-civil by Derwick-as sold
Bid Due Date:
Item |  | Description |  |  |  | No. | Cost | Total
No. | [5 empty] | Units | Per Unit | Cost
1
2 | Project & Construciton Management
3 | R T Air Fares |  |  |  |  | 100 | 2500 | 250000
4 | Months of Per Diem at Site (Mgt) |  | Assumes Apartment Rental, meals, etc. |  |  | 100 | 3000 | 300000
5 | Number of Months of Pick Up Trucks |  |  |  |  | 20 | 2500 | 50000
6 | Misc expenditures |  |  |  |  | 1 | 125000 | 125000
7 | Days Per Diem - Lodging & Meals (Techs) |  |  |  |  | 2000 | 52 | 104000
8
9
10
11
12
13 | Engineering
14 | Round Trip Air Fare for Eng Visits to site |  |  |  |  | 15 | 2500 | 37500
15 | Days of Per Diem Cost for Eng Days at Site |  |  |  |  | 150 | 175 | 26250
16 | Auto Rental for Eng Days at Site |  |  |  |  | 0 | 0 | 0
17 | Misc Travel Expentitures |  |  |  |  | 0 | 0 | 0
18
19
20 |  |  |  |  | Total Cost of Project Mgt Tvl and Per Diem |  |  | 892.75
21
22
23
24 | Engineering Meal Expense |  |  |  |  | 0 | 50 | 0 | 0
25
26 | Project Mgt Meal Expense |  |  |  |  | 0 | 50 | 0 | 0
27
28 |  |  |  |  | Total Meal Expense |  |  | 0
29
30
31
32
33
34
35
36