## Sheet1
Hawaii/Pacific Islands CCP Document Development Milestones
|  | Preplanning |  | Scoping |  | Alternatives |  | Internal & Public Review |  |  | CCP Finalization
Refuge/Complex | Lead Planner | Initiate Preplanning | Preplanning Report | FR NOI | Scoping Briefing Statement | Draft Goals & Objectives | Alternatives Briefing Statement | Internal Review Draft | FR NOA Draft CCP | Draft CCP & Public Review | Final CCP Briefing Statement | FR NOA Final CCP (EA-FONSI) | Final CCP (ROD if required)
PLANS UNDERWAY
Howland | Pelizza | Oct 2004 | n/a | Sept 2005 | Dec 2005 | Feb 2006 | Mar 2006 | Sept 2006 | Aug2007 | Sept 2007 | Nov 2007 | Dec 2007 | Dec 2007
Baker | Pelizza | Oct 2004 | n/a | Sept 2005 | Dec 2005 | Mar 2006 | July 2006 | Feb 2007 | Aug2007 | Sept 2007 | Nov 2007 | Dec 2007 | Dec 2007
Jarvis | Pelizza | Oct 2004 | n/a | Sept 2005 | Dec 2005 | Mar 2006 | July 2006 | Feb 2007 | Aug2007 | Sept 2007 | Nov 2007 | Dec 2007 | Dec 2007
Palmyra Atoll | Smith | Feb 2006 | Dec 2007 | Jan 2008 | Mar 2008 | Apr 2008 | June 2008 | July 2008 | Nov 2008 | Dec 2008 | Mar 2009 | Apr 2009 | Apr 2009
Guam | Ha | July 2006 | Mar 2007 | Apr 2007 | Jun 2007 | Oct 2007 | Nov 2007 | Mar 2008 | July 2008 | Aug 2008 | Oct 2008 | Nov 2008 | Dec 2008
Kealia Pond | Pelizza | Sept 2006 | Aug 2007 | Sept 2007 | Nov 2007 | May 2008 | Aug 2008 | Dec 2008 | May 2009 | July 2009 | Sept 2009 | Dec 2009 | Feb 2010
Kakahaia | Pelizza | Sept 2006 | Aug 2007 | Sept 2007 | Nov 2007 | May 2008 | Aug 2008 | Dec 2008 | May 2009 | July 2009 | Sept 2009 | Dec 2009 | Feb 2010
PRE-PLANNING BEGINNING IN FY07
Midway | NM mgr | Jan 2007 | Feb 2007* | Mar 2007 | July 2007 | Sept 2007 | Nov 2007 | Dec 2007 | Mar 2008 | Apr 2008 | June 2008 | July 2008 | July 2008
NW Hawaiian Is | NM mgr | Jan 2007 | Feb 2007* | Mar 2007 | July 2007 | Sept 2007 | Nov 2007 | Dec 2007 | Mar 2008 | Apr 2008 | June 2008 | July 2008 | July 2008
Kingman Reef | Smith | Feb 2006 | Dec 2008 | Jan 2009 | Mar 2009 | Apr 2009 | June 2009 | July 2009 | Nov 2009 | Dec 2009 | Mar 2010 | Apr 2010 | Apr 2010
J. Campbell | Pelizza | Jan 2007 | Nov 2007 | Dec 2007 | Apr 2008 | Sept 2008 | Feb 2009 | June 2009 | Sept 2009 | Nov 2009 | Jan 2010 | Mar 2010 | May 2010
Pearl Harbor | Pelizza | Jan 2007 | Nov 2007 | Dec 2007 | Apr 2008 | Sept 2008 | Feb 2009 | June 2009 | Sept 2009 | Nov 2009 | Jan 2010 | Mar 2010 | May 2010
PRE-PLANNING BEGINNING IN FY08
Hakalau Forest | Ha | Oct 2007 | May 2008 | June 2008 | Sept 2008 | Mar 2009 | Aug 2009 | Dec 2009 | Mar 2010 | Apr 2010 | June 2010 | Aug 2010 | Oct 2010
Huleia | Pelizza | Oct 2007 | Mar 2008 | Apr 2008 | July 2008 | Jan 2009 | June 2009 | Oct 2009 | Mar 2010 | May 2010 | July 2010 | Oct 2010 | Dec 2010
Hanalei | Pelizza | Oct 2007 | Mar 2008 | Apr 2008 | July 2008 | Jan 2009 | June 2009 | Oct 2009 | Mar 2010 | May 2010 | July 2010 | Oct 2010 | Dec 2010
Kilauea Point | Pelizza | Oct 2007 | Mar 2008 | Apr 2008 | July 2008 | Jan 2009 | June 2009 | Oct 2009 | Mar 2010 | May 2010 | July 2010 | Oct 2010 | Dec 2010
PRE-PLANNING BEGINNING IN FY09
Rose Atoll | Pelizza | Apr 2009 | Nov 2009 | Dec 2009 | Apr 2010 | Sept 2010 | Feb 2011 | June 2011 | Sept 2011 | Nov 2011 | Jan 2012 | Mar 2012 | May 2012
PRE-PLANNING BEGINNING IN FY10
Johnston Isl. | Pelizza | Oct 2009 | Mar 2010 | Apr 2010 | Aug 2010 | Jan 2011 | Jun 2011 | Oct 2011 | Jan 2012 | Mar 2012 | May 2012 | Jul 2012 | Sept 2012
Oahu Forest | Ha | Jan 2010 | Aug 2010 | Oct 2010 | Jan 2011 | Apr 2011 | July 2011 | Nov 2011 | Mar 2012 | May 2012 | July 2012 | Sept 2012 | Sept 2012
Note: PrePlanning is initiated on the 1st of the Month and Preplanning Reports are due on the 1st of the Month; Internal Reviews are to target starting at the beginning of the Month and be completed within that month; All other Milestones should be completed prior to the end of the target month.
* Note: CCPs part of NW Hawaiian Island National Monument Management Plan; pre-planning requirements include Work Plan and Communications Plan