## Sheet1
Pacific NW CCP Document Development Milestones
|  |  | Preplanning |  | Scoping |  | Alternatives |  | Internal & Public Review |  |  | CCP Finalization
Refuge/Complex | Lead Planner | GIS Point of Contact | Initiate Pre-planning | Pre-planning Report | FR NOI | Scoping Briefing Statement | Draft Goals & Objectives | Alternatives Briefing Statement | Internal Review Draft | FR NOA Draft CCP | Draft CCP & Public Review | Final CCP Briefing Statement | FR NOA Final CCP (EA-FONSI) | Final CCP (ROD if re-quired)
PLANS UNDERWAY
Turnbull NWR | Selvaggio | Drescher | May 1999 | n/a | Mar 2000 | May 2003 | May 2001 | May 2003 | Mar 2003 | June 2005 | June 2005 | May 2006 | Mar 2007 | Mar 2007
Washingon Islands | Bardolf | So | Began | n/a | Mar 2000 | Oct 2003 | n/a | Oct 2003 | July 2001 | Sept 2004 | May 2005 | Aug 2006 | Sept 2006 | Sept 2006
Hanford Reach NM | Haas | Hoy | Began | n/a | June 2002 | May 2003 | June 2005 | Feb 2006 | June 2006 | Oct 2006 | Jan 2007 | July 2007 | Nov 2007 | Dec 2007
McNary & Umatilla | Selvaggio | Maty | June 2003 | n/a | May 2004 | Oct 2005 | June 2005 | June 2006 | May 2006 | Nov 2006 | Jan 2007 |  | May 2007 | May 2007
Protection Island NWR | Bardolf | So | June 2004 | Feb 2007 | July 2007 | Nov 2007 | Jan 2008 | Mar 2008 | June 2008 | Oct 2008 | Oct 2008 | Feb 2009 | Apr 2009 | Apr 2009
San Juan Island NWR | Bardolf | So | June 2004 | Feb 2007 | July 2007 | Nov 2007 | Jan 2008 | Mar 2008 | June 2008 | Oct 2008 | Oct 2008 | Feb 2009 | Apr 2009 | Apr 2009
Ridgefield NWR | Morris | Maty | Summer 2005 | Mar 2006 | June 2006 | Oct 2006 | Jan 2007 | June 2007 | Oct 2007 | Mar 2008 | May 2008 | July 2008 | Oct 2008 | Dec 2008
Julia Butler Hanson NWR | Young | So | Oct 2005 | Mar 2006 | Sept 2006 | Nov 2006 | Jan 2007 | May 2007 | Sept 2007 | Feb 2008 | Apr 2008 | June 2008 | Sept 2008 | Nov 2008
Lewis & Clark NWR | Young | So | Oct 2005 | Mar 2006 | Sept 2006 | Nov 2006 | Jan 2007 | May 2007 | Sept 2007 | Feb 2008 | Apr 2008 | June 2008 | Sept 2008 | Nov 2008
Cape Meares NWR | Harrison | So | Jan 2006 | Aug 2006 | Sept 2006 | Jan 2007 | June 2007 | Nov 2007 | Mar 2008 | June 2008 | Aug 2008 | Oct 2008 | Dec 2008 | Feb 2009
Oregon Islands NWR | Harrison | So | Jan 2006 | Aug 2006 | Sept 2006 | Jan 2007 | June 2007 | Nov 2007 | Mar 2008 | June 2008 | Aug 2008 | Oct 2008 | Dec 2008 | Feb 2009
Three Arch Rocks NWR | Harrison | So | Jan 2006 | Aug 2006 | Sept 2006 | Jan 2007 | June 2007 | Nov 2007 | Mar 2008 | June 2008 | Aug 2008 | Oct 2008 | Dec 2008 | Feb 2009
Sheldon NWR | Goheen | Hoy | Feb 2006 | July 2007 | Sept 2007 | Dec 2007 | May 2008 | Sept 2008 | Jan 2009 | Apr 2009 | July 2009 | Nov 2009 | Feb 2010 | May 2010
PRE-PLANNING BEGINNING IN FY07
Ankeny NWR | Selvaggio | So | Oct 2006 | July 2007 | Sept 2007 | Jan 2008 | June 2008 | Dec 2008 | May 2009 | Aug 2009 | Nov 2009 | Jan 2010 | May 2010 | July 2010
Basket Slough NWR | Selvaggio | Maty | Oct 2006 | July 2007 | Sept 2007 | Jan 2008 | June 2008 | Dec 2008 | May 2009 | Aug 2009 | Nov 2009 | Jan 2010 | May 2010 | July 2010
William L. Finley NWR | Selvaggio | So | Oct 2006 | July 2007 | Sept 2007 | Jan 2008 | June 2008 | Dec 2008 | May 2009 | Aug 2009 | Nov 2009 | Jan 2010 | May 2010 | July 2010
Columbia NWR | Haas | Hayes | Jan 2007 | Sept 2007 | Nov 2007 | Apr 2008 | Sept 2008 | Jan 2009 | May 2009 | Aug 2009 | Nov 2009 | Dec 2009 | Feb 2010 | Feb 2010
Willapa NWR | Young | So | July 2007 | Dec 2007 | Feb 2008 | Apr 2008 | Sept 2008 | Feb 2009 | June 2009 | Sept 2009 | Nov 2009 | Jan 2010 | Apr 2010 | June 2010
PRE-PLANNING BEGINNING IN FY08
Cold Springs NWR | Haas | Hayes | Oct 2007 | Mar 2008 | May 2008 | Aug 2008 | Jan 2009 | June 2009 | Oct 2009 | Jan 2010 | Mar 2010 | May 2010 | July 2010 | Sept 2010
McKay Creek NWR | Haas | Hayes | Oct 2007 | Mar 2008 | May 2008 | Aug 2008 | Jan 2009 | June 2009 | Oct 2009 | Jan 2010 | Mar 2010 | May 2010 | July 2010 | Sept 2010
Kootentai NWR | Morris | Hayes | Oct 2007 | Mar 2008 | May 2008 | Aug 2008 | Jan 2009 | June 2009 | Oct 2009 | Jan 2010 | Mar 2010 | May 2010 | July 2010 | Sept 2010
Dungeness NWR (POC) | Bardolf | So | Nov 2007 | May 2008 | July 2008 | Nov 2008 | Apr 2009 | Sept 2009 | Jan 2010 | Apr 2010 | June 2010 | Aug2010 | Oct 2010 | Dec 2010
Deer Flat NWR | Morris | Maty | Jan 2008 | Aug 2008 | Oct 2008 | Jan 2009 | June 2009 | Nov 2009 | Mar 2010 | June 2010 | Aug 2010 | Oct 2010 | Dec 2010 | Feb 2011
Minidoka NWR | Morris | Maty | Jan 2008 | Aug 2008 | Oct 2008 | Jan 2009 | June 2009 | Nov 2009 | Mar 2010 | June 2010 | Aug 2010 | Oct 2010 | Dec 2010 | Feb 2011
Bandon Marsh NWR | Bardolf | So | Aug 2008 | Apr 2009 | June 2009 | Oct 2009 | Feb 2010 | July 2010 | Nov 2010 | Feb 2011 | Apr 2011 | June 2011 | Sept 2011 | Nov 2011
Nestucca Bay NWR | Bardolf | So | Aug 2008 | Apr 2009 | June 2009 | Oct 2009 | Feb 2010 | July 2010 | Nov 2010 | Feb 2011 | Apr 2011 | June 2011 | Sept 2011 | Nov 2011
Siletz Bay NWR | Bardolf | So | Aug 2008 | Apr 2009 | June 2009 | Oct 2009 | Feb 2010 | July 2010 | Nov 2010 | Feb 2011 | Apr 2011 | June 2011 | Sept 2011 | Nov 2011
PRE-PLANNING BEGINNING IN FY09
Hart Mountain NAR | Goheen | Hoy | Nov 2008 | July 2009 | Sept 2009 | Dec 2009 | May 2010 | Sept 2010 | Jan 2011 | Apr 2011 | July 2011 | Nov 2011 | Feb 2012 | May 2012
Malheur NWR | Selvaggio | Hoy | Jan 2009 | Aug 2009 | Oct 2009 | Jan 2010 | June 2010 | Dec 2010 | Feb 2011 | May 2011 | July 2011 | Dec 2011 | Apr 2012 | Aug 2012
Bear Lake NWR | Morris | Maty | May 2009 | Mar 2010 | May 2010 | Sept 2010 | Feb 2011 | July 2011 | Nov 2011 | Jan 2012 | Mar 2012 | May 2012 | July 2012 | Sept 2012
Camas NWR | Morris | Maty | May 2009 | Mar 2010 | May 2010 | Sept 2010 | Feb 2011 | July 2011 | Nov 2011 | Jan 2012 | Mar 2012 | May 2012 | July 2012 | Sept 2012
Grays Lake NWR | Morris | Maty | May 2009 | Mar 2010 | May 2010 | Sept 2010 | Feb 2011 | July 2011 | Nov 2011 | Jan 2012 | Mar 2012 | May 2012 | July 2012 | Sept 2012
Oxford Slough WPA | Morris | Maty | May 2009 | Mar 2010 | May 2010 | Sept 2010 | Feb 2011 | July 2011 | Nov 2011 | Jan 2012 | Mar 2012 | May 2012 | July 2012 | Sept 2012
Black River (Nisqually) | Young | So | Aug 2009 | Mar 2010 | Apr 2010 | Aug 2010 | Dec 2010 | May 2011 | Sept 2011 | Dec 2011 | Feb 2012 | Apr 2012 | June 2012 | Aug 2012
Grays Harbor NWR | Young | So | Aug 2009 | Mar 2010 | Apr 2010 | Aug 2010 | Dec 2010 | May 2011 | Sept 2011 | Dec 2011 | Feb 2012 | Apr 2012 | June 2012 | Aug 2012
Tualatin River NWR | Harrison | So | Sept 2009 | Mar 2010 | May 2010 | Sept 2010 | Feb 2011 | July 2011 | Nov 2011 | Feb 2012 | Mar 2012 | June 2012 | Aug 2012 | Sept 2012
PRE-PLANNING BEGINNING IN FY10
Conboy Lake NWR | Haas | Maty | Oct 2009 | Mar 2010 | Apr 2010 | June 2010 | Dec 2010 | Apr 2011 | July 2011 | Jan 2012 | Mar 2012 | Sept 2012 | Nov 2012 | Dec 2012
Toppenish NWR | Haas | Hayes | Oct 2009 | Mar 2010 | Apr 2010 | June 2010 | Dec 2010 | Apr 2011 | July 2011 | Jan 2012 | Mar 2012 | Sept 2012 | Nov 2012 | Dec 2012