Cultural Resources Contract

**EXAMPLE**
Cypress Creek NWR
SCOPE OF SERVICE

Overview study and predictive model of cultural resources on Cypress Creek National Wildlife Refuge in Alexander, Johnson, Pulaski, and Union Counties, Illinois.

Table of Contents:

- Introduction

- Background and Relationships

- Overview Study

- Illustrations and Maps

- Curation

- Contacts and Permits

- Due Dates

- Technical Report Format

- Proposal

Attachment I: Form 272 “Report Documentation Page” Attachment II: National Archaeological Data Base Report Attachment III: Maps

Attachment IV: Technical Report Format

Attachment V. Detailed Cost Proposal

1.	INTRODUCTION:

1.1 FWS (U.S. Fish and Wildlife Service, Region 3) proposes to meet its cultural resources management responsibilities through compliance with the National Historic Preservation Act as amended by contracting for a cultural resources overview study. This scope of service is designed to provide guidance to the contractor.

1.1.1 Cultural resource overview is a comprehensive document prepared for a field office that discusses, among other things, its prehistory and cultural history, the nature and extent of known cultural resources, previous research, management objectives, resource management conflicts or issues, and a general statement on how program objectives should be met and conflicts resolved. An overview should reference or incorporate information from a field office’s background or literature search. (614 FW 1.7D)

1.1.2 Background or literature search, the most general level of cultural resource identification, consists of a thorough search of the professionals historical, architectural, and archeological literature for a given area; the cultural resource files of State HPOs and state historic and archeological property surveys; files of local or county agencies or societies, where they exist; the list of properties in or eligible for listing in the National Register of Historic Places; published and unpublished histories; old maps. Other sources may be used to provide information on the location, nature, extent, number and distribution of known cultural resources within the area. This process identifies specific properties for consideration, and is a necessary first step in assessing the probability of finding properties that have not yet been identified. (CRMH VIII.B.1)

1.1 Questions regarding technical aspects of this study should go to RHPO (Regional Historic
Preservation Officer, John Dobrovolny, FWS). The phone number is (612) 725-3693.

1.2 The contract might be amended for reasons required by this scope of service or other developments. Only the Contracting Officer can make changes to this contract that may result in an increase or decrease in the contract price or to any of the terms and conditions contained therein.

1.3 The final product will be a comprehensive, professional quality technical report detailing the results of this study.

2.	BACKGROUND AND RELATIONSHIPS:

2.1 The Refuge Manager, Cypress Creek NWR, is proposing to develop a Comprehensive Management Plan of the refuge in accordance with the Fish and Wildlife Manual Part 602, Comprehensive Management Planning. The Comprehensive Management Plan is to include “the archaeological and cultural values of the planning unit.”

2.2 Cypress Creek NWR was established in 1990 and is projected to incorporate approximately 35,200 acres in the Illinois counties of Alexander, Johnson, Pulaski, and Union. Approximately one-third of the land has been acquired.

2.2.1 The overview study area encompasses all the land within the Refuge boundaries regardless of ownership, plus a contextual zone around the Refuge that extends outward at least 5 miles from the Refuge boundaries.

2.3 The Advisory Council of Historic Preservation supports Illinois Historic Preservation Officer’s request for survey as the basis for planning and management of Refuge cultural resources, and recommended a programmatic agreement. The SHPO objected to the compliance process described in the Refuge establishment Environmental Assessment and requested schedule for archeological survey of the entire refuge.

3.	OVERVIEW STUDY:

3.1 Inspect the cultural resources records and data of the State Historic Preservation Officer, Illinois Department of Conservation, Illinois Department of Transportation, schools and museums in the state with applicable records, local historical and preservation societies and organizations, and Federal agencies such as the Army Corps of Engineers, Forest Service, and Natural Resources Conservation Service for information applicable to the study area. Include in the report a list of all the agencies and offices contacted and the results of those contacts, even if negative.

3.2 Inspect written archival sources such as the National Register of Historic Places, state site files, USGS maps, 19th ‘20th century plat maps, and Government Land Office surveys for information applicable to the study area. Include in the report a list of all the sources inspected and the results even if negative. Using published geological references and other sources, evaluate and describe in the report the potential for buried soil horizons containing cultural resources.

3.3 Conduct oral interviews with local collectors, former and current property owners, and local historical society members. Include in the report a list of all the sources contacted and the results even if negative.

3.4 Describe all reported archeologists within the study area. At a minimum include their legal location (¼ ¼ ¼ Section, Township, Range), type, and description; cross-reference to and plot on county or USGS map(s) by use of the site numbers; and place in an appendix clearly marked “Not for Publication.”

3.5 Synthesize the history and prehistory of the study area; not rote recitations, but characterize the historic and prehistoric activities that are most likely to have left evidence of their existence within the Refuge, and predict how such evidence may appear today.

3.6 Take into account any preservation planning of a larger scale applicable to the study area. Where a larger scale plan has been officially adopted, excerpt from the plan to the extent applicable; this overview should either be consistent with the plan or provide a clear rationale for inconsistencies.

3.7 Describe and evaluate the quality of the archeological, anthropological, historical, and other studies and data bases upon which knowledge of the area’s history and prehistory are based. Identify gaps in the knowledge base, identify any biases that may have characterized prior work and hence biased the data base and identify the data needed to fill knowledge gaps or to correct biases.

3.8 Identify the classes of properties having possible archeological or historical value that are expected to occur within the Refuge.

3.9 Identify, preferably ranked in priority order, the scientific and humanistic research questions that are likely to be addressed through study of the Refuge area history and prehistory. Justify the importance of addressing each question in the public interest. Identify those classes of properties likely found within the Refuge expected to contain data applicable to important research questions.

3.10 Identify for each class of properties relevant to one or more research questions, the expected numbers, densities, and distributions of properties within the Refuge. The factual and analytic bases for each prediction must be specified. An active model for archeological and historic properties on the Refuge, identifying areas of high, moderate, and low potential for the presence of significant cultural resources. Evaluate the hypothesis that archeological sites are not likely to be found below a certain elevation within the Refuge.

3.11 Identify organizations, local governments, and social or ethnic groups with interest in or concerns about the historical and cultural values of the Refuge area, and define the historical and cultural issues of concern. Identify reasonable methods for obtaining and taking into account the views of groups interested in the cultural values of the Refuge.

3.12 Identify known locations of religious importance to American Indians, and establish reasonable methods to identify such locations that are not known at the present time.

- ILLISTRATIONS AND MAPS:

4.1 Line drawings and maps shall be clean, clear, and easily reproducible. Maps will be north-oriented to the top of the page, and will contain appropriate scale and keys.

4. 1.1 An overview summary map will be prepared at a scale not to exceed one kilometer to a centimeter.

4.1.2 Individual base maps representing the resource in accurate proportions and position will be prepared at a maximum scale of 25 meters to the centimeter (approximately ¼ ¼ section on a page). All base maps will be to the same scale.

4.2 Base maps will clearly locate the study areas. Study results will be located on maps with clear cross-referencing to narrative, charts, and lists.

4.3 Include maps showing the location of the Refuge within the region, the areas within the Refuge that have been previously subjected to archeological survey, with indications of the intensity and quality of each survey, the locations of each known archeological and historic property with an indication of status (i.e., National Register nomination, determination, eligibility), projected property distributions, and appropriate ethnographic, geographic, geological, and ecological data.

- CURATION:

5.1 Locate and identify collections of archeological materials taken from the Refuge, including collections made before Refuge establishment. Include materials in institutional repositories (e.g., museums, schools, and contract archeologists) and in private collections. An inventory of these materials is not desired. But provide a general description of the materials in each collection, examples of diagnostic or otherwise important items, the location of the site from which the artifacts were taken, availability of the collection by researchers, condition of the stored material, accessioning and cataloging systems, linear feet of documents, approximate number of artifacts, and cubic feet of artifacts.

- CONTACTS AND PERMITS:

6.1 Upon completion of fieldwork, meet with the manager and staff to inform them of tentative results of the study.

6.2 The contractor shall initiate no contacts with the media for the purpose of disseminating information relating to the contract until the final report is approved. Questions shall have to be referred to the RHPO.

6.3 FWS will distribute the technical report to the State Historic Preservation Officer and other appropriate parties. Contractor will make no independent distribution of interim, letter, draft, or final reports until final report is approved.

6.4 The principle investigator and key personnel are required to meet the minimum standards as specified in federal Guidelines, Title 36, Code of Federal Regulations, Part 66, Appendix C.

- DUE DATES:

7.1 Work will be completed in accordance with the following time schedule, unless other arrangements are made in advance with the RHPO and approved by the Contracting Officer. If another schedule is desired, propose it as an alternative. All dates are calendar days from the purchase order or contract date.

Commence literature search:	20

Submit draft report:	90

7.2 Draft report will be complete when submitted, with sufficient accuracy such that it is likely to be accepted as a final report without revision. Machine copies of photographs in the draft report are acceptable. The draft report will be submitted in three copies to RHPO.

7.3 If revisions are required, the contractor will supply a revised draft report for review at no additional costs to the government. It will be completed and provided to the government within 30 days from the date of notice by the Contracting Officer.

7.4 Final report will be submitted in 15 copies within 30 calendar days of notification by the contracting Officer. Reports will be securely bound at left margin; one report will be submitted unbound.

- TECHNICAL REPORT FORMAT:

8.1 Format of the technical report will be tailored to the content of the report.

8.2 Report shall be single-spaced (per NTIS requirement) typewritten on good quality bond
paper, 8.5” by 11” with 1.5” margin at left and bottom, 1” margin at top and right.

8.3 Narrative will employ correct English grammar, with no typographical errors.

8.4 All pages will be numbered consecutively including bibliography and attachments.

8.5 Record all measurements using the English and metric systems.

8.6 The contractor will provide a completed “National Archeological Data Base Report Recording/Updated Form, Version 2.01G” along with but not bound with the draft and final technical reports.

9.	PROPOSAL:

9.1 The contractor shall conduct this study in a manner that insures the greatest contribution to an understanding of state prehistory and history. In an effort to ensure this quality, prospective principal investigators shall submit a short technical research proposal, which shall include sufficient discussion to describe how the needs of this study will be met. Proposal shall be organized around and follow the same order as paragraphs 11.1.1 – 11.1.3 of this section. Use the attached detailed cost proposal form for presenting the budget.

9.1.1 The proposal shall name the principal investigator, archeologist, historian, and key personnel and illustrate how they meet the minimum standards as specified in Federal Guidelines, Title 36, Code of Federal Regulations, Part 66, Appendix C. Attachment of “canned” vitae will not be sufficient.

9.1.2 The proposal must demonstrate knowledge of previous work in the region by including a research design and the objectives that will guide the study and measure effectiveness of results. The proposal will also include a list of contacts, documents, and institutions likely to be used in the literature search.

9.1.3 Proposal shall include a tentative schedule of the major phases of the study including anticipated submission of the draft report. Also, if the contractor considers the study can be better accomplished in a manner different from this scope of service, the contractor should include a recommended alternative approach that he/she would follow.

9.2 Consultants hired or subcontracted for their special knowledge and expertise must carry academic and experiential qualifications in their own fields of competence equivalent to those of an archeologist or historian are to be documented by attachments to the proposal or at a later time if the consultant has not been retained at the time of the proposal.

9.3 If any items in the scope of service need to be modified to accommodate a viable proposal (e.g., change in due dates), present alternatives for consideration.

9.4 Any proposal or vitae submitted for similar work at this refuge within the past two years need not be resubmitted. Minor changes needed to update the proposal or vitae may be submitted as an amendment. Methods used to reduce cost to the government such as inclusion in the report being prepared for previous work at the refuge, even if the report being prepared must be delayed, should be described.

9.5 Any questions regarding this scope of work and the likelihood that it will yield a professional archeological study should be directed to the RHPO before the date set for receipt of quotations.

Attachment IV. Report Format

A.	Title Page

- Name of Project, short and succinct

- Prepared for: Department of the Interior, U.S. Fish and Wildlife Service

- Contract or purchase order number

- Study dates

- Report submittal date

- Prepared  by

- Name of principal investigator

B.	Form 272 “Report Documentation Page” in duplicate

- Complete  sections 4,5,7,8,9,11,12,13,15,16,17,18,and 21

- Abstract:  Prepared by the Principal Investigator, describing the overall research context of the report, the significance of the work, and any other related background circumstances relating to the manner in which the work was undertaken.

- Acknowledgements: List type of support the investigator received, as well as to indicate where credit might be due.

- Table of Contents

- List of Illustrations (if any)

- Body of Report

- Introduction: Project scope, location, individuals involved, etc.

- Research  objectives

- Environmental background and existing conditions: Physiographic region, soils, vegetation, and ethnographic and historic background.

- Base maps locating study area, sites, and areas of disturbance.

- Study methodology and procedures.

- In one section present findings, conclusions, recommendations, statements of significance, future research questions. Tie results directly to the research objectives. Describe the predictive model and the probability for buried and missed sites.

- Describe how the study met or failed to meet objectives of the research design, descriptive analytic and interpretive techniques and summaries of classification systems used, and quantitative techniques used to interpret data.

- Adequately footnote sources of information.

G.	Bibliography

- Literature search and records review

- Persons interviewed

- Negative  as well as positive results

H.	Appendices

- Scope of service

- Research  design proposal

- Basic qualifications of investigators

- Formal For correspondence

- List and description of artifacts

- Site  location maps and individual site forms not appropriate for publishing, marked “Not Submitted to NPS/NTIS.”

- Any  other important data not directly applicable to the narrative